## Detailed Calc (hidden)
Detailed BOQ
Items
|  |  | Length (m) | Width (m) | Hight (m) | Quantity | Unit
1 | Site Work
| Site Preparation |  | 30.2 | 13.8 |  | 1 | LS
2 | Earth Work
2.1 | Excavation | [8 empty] | Center to center length of the axes
2.1.1 | Foundation | [7 empty] | Consd L | L | W | H | Length Add/Sub
|  | A | 23.4 | 1 | 0.8 | 18.72 |  |  | 23.4 | 22.4 | 1 | 0.8 | 1
|  | B | 23.4 | 1 | 0.8 | 18.72 |  |  | 23.4 | 22.4 |  |  | 1
|  | C | 30.4 | 1 | 0.8 | 24.32 |  |  | 30.4 | 29.4 |  |  | 1
|  | D | 30.4 | 1 | 0.8 | 24.32 |  |  | 30.4 | 29.4 |  |  | 1
|  | 1 | 3.65 | 1 | 0.8 | 2.92 |  |  | 3.65 | 4.65 |  |  | 1
|  | 2 | 5 | 1 | 0.8 | 4 |  |  | 5 | 7 |  |  | 2
|  | 3 | 3.65 | 1 | 0.8 | 2.92 |  |  | 3.65 | 4.65 |  |  | 1
|  | 4 | 3.65 | 1 | 0.8 | 2.92 |  |  | 3.65 | 4.65 |  |  | 1
|  | 5 | 3.65 | 1 | 0.8 | 2.92 |  |  | 3.65 | 4.65 |  |  | 1
|  | 6 | 4.25 | 1 | 0.8 | 3.4 |  |  | 4.25 |  |  |  | 1
|  | 7 | 3.65 | 1 | 0.8 | 2.92 |  |  | 3.65 | 4.65 |  |  | 1
|  | 8 | 3.65 | 1 | 0.8 | 2.92 |  |  | 3.65 | 4.65 |  |  | 1
|  | 9 | 5 | 1 | 0.8 | 4 |  |  | 5 | 7 |  |  | 2
|  | 10 | 3.65 | 1 | 0.8 | 2.92 |  |  | 3.65 | 4.65 |  |  | 1
| Second Axis | 1 | 1.55 | 0.7 | 0.8 | 0.87 |  |  | 1.55 | 2.55 | 0.7 | 0.8 | 1
|  | 2 | 1.35 | 0.7 | 0.8 | 0.76 |  |  | 1.35 | 2.35 |  |  | 1
|  | 3 | 1.35 | 0.7 | 0.8 | 0.76 |  |  | 1.35 | 2.35 |  |  | 1
2.1.2 | Stairs
|  | 1 | 6 | 1.7 | 0.2 | 2.04 | [5 empty] | 0.2
|  | 2 | 2 | 0.9 | 0.2 | 0.36
|  | 3 | 2 | 0.9 | 0.2 | 0.36
2.1.3 | Walkway |  | 87.77 | 0.7 | 0.2 | 12.29 | [5 empty] | 0.2
2.1.4 | Ramp | 1 | 5.1 | 1 | 0.2 | 1.02
| Excavation |  |  |  | Total | 136.38 | m3
2.2 | Backfilling | [8 empty] | Center to center length of the axes
2.2.1 | Foundation | [7 empty] | Consd L | L | W | H | Length Add/Sub
| Main Axes | A | 23.4 | 0.2 | 0.8 | 3.74 |  |  | 23.4 | 22.4 | 1 | 0.8 | 1
|  | B | 23.4 | 0.2 | 0.8 | 3.74 |  |  | 23.4 | 22.4 | 0.2 |  | 1
|  | C | 30.4 | 0.2 | 0.8 | 4.86 |  |  | 30.4 | 29.4 |  |  | 1
|  | D | 30.4 | 0.2 | 0.8 | 4.86 |  |  | 30.4 | 29.4 |  |  | 1
|  | 1 | 3.65 | 0.2 | 0.8 | 0.58 |  |  | 3.65 | 4.65 |  |  | 1
|  | 2 | 5 | 0.2 | 0.8 | 0.8 |  |  | 5 | 7 |  |  | 2
|  | 3 | 3.65 | 0.2 | 0.8 | 0.58 |  |  | 3.65 | 4.65 |  |  | 1
|  | 4 | 3.65 | 0.2 | 0.8 | 0.58 |  |  | 3.65 | 4.65 |  |  | 1
|  | 5 | 3.65 | 0.2 | 0.8 | 0.58 |  |  | 3.65 | 4.65 |  |  | 1
|  | 6 | 4.25 | 0.2 | 0.8 | 0.68 |  |  | 4.25 |  |  |  | 1
|  | 7 | 3.65 | 0.2 | 0.8 | 0.58 |  |  | 3.65 | 4.65 |  |  | 1
|  | 8 | 3.65 | 0.2 | 0.8 | 0.58 |  |  | 3.65 | 4.65 |  |  | 1
|  | 9 | 5 | 0.2 | 0.8 | 0.8 |  |  | 5 | 7 |  |  | 2
|  | 10 | 3.65 | 0.2 | 0.8 | 0.58 |  |  | 3.65 | 4.65 |  |  | 1
| Second Axis | 1 | 1.55 | 0.2 | 0.8 | 0.25 |  |  | 1.55 | 2.55 | 0.2 | 0.8 | 1
|  | 2 | 1.35 | 0.2 | 0.8 | 0.22 |  |  | 1.35 | 2.35 |  |  | 1
|  | 3 | 1.35 | 0.2 | 0.8 | 0.22 |  |  | 1.35 | 2.35 |  |  | 1
2.2.2 | Stairs
|  | 1 | 6 | 0.2 | 0.2 | 0.24 | [5 empty] | 0.2
|  | 2 | 2 | 0.2 | 0.2 | 0.08
|  | 3 | 2 | 0.2 | 0.2 | 0.08
2.2.3 | Walkway |  | 87.77 | 0.2 | 0.2 | 3.51 | [5 empty] | 0.2
2.2.4 | Ramp | 1 | 5.1 | 0.2 | 0.2 | 0.2
| Backfilling |  |  |  | Total | 28.34 | m3
3 | Stone Masonry Work
3.1 | Foundation | [8 empty] | Center to center length of the axes
3.1.1 | Stone Masonry along Axes | [7 empty] | Consd L | L | W | H | Length Add/Sub
| Main Axes | A | 23.2 | 0.8 | 0.8 | 14.85 |  |  | 23.2 | 22.4 | 0.8 | 0.8 | 1
|  | B | 23.2 | 0.8 | 0.8 | 14.85 |  |  | 23.2 | 22.4 |  |  | 1
|  | C | 30.2 | 0.8 | 0.8 | 19.33 |  |  | 30.2 | 29.4 |  |  | 1
|  | D | 30.2 | 0.8 | 0.8 | 19.33 |  |  | 30.2 | 29.4 |  |  | 1
|  | 1 | 3.85 | 0.8 | 0.8 | 2.46 |  |  | 3.85 | 4.65 |  |  | 1
|  | 2 | 5.4 | 0.8 | 0.8 | 3.46 |  |  | 5.4 | 7 |  |  | 2
|  | 3 | 3.85 | 0.8 | 0.8 | 2.46 |  |  | 3.85 | 4.65 |  |  | 1
|  | 4 | 3.85 | 0.8 | 0.8 | 2.46 |  |  | 3.85 | 4.65 |  |  | 1
|  | 5 | 3.85 | 0.8 | 0.8 | 2.46 |  |  | 3.85 | 4.65 |  |  | 1
|  | 6 | 4.25 | 0.8 | 0.8 | 2.72 |  |  | 4.25 |  |  |  | 1
|  | 7 | 3.85 | 0.8 | 0.8 | 2.46 |  |  | 3.85 | 4.65 |  |  | 1
|  | 8 | 3.85 | 0.8 | 0.8 | 2.46 |  |  | 3.85 | 4.65 |  |  | 1
|  | 9 | 5.4 | 0.8 | 0.8 | 3.46 |  |  | 5.4 | 7 |  |  | 2
|  | 10 | 3.85 | 0.8 | 0.8 | 2.46 |  |  | 3.85 | 4.65 |  |  | 1
| Second Axis | 1 | 1.75 | 0.5 | 0.8 | 0.7 |  |  | 1.75 | 2.55 | 0.5 | 0.8 | 1
|  | 2 | 1.55 | 0.5 | 0.8 | 0.62 |  |  | 1.55 | 2.35 |  |  | 1
|  | 3 | 1.55 | 0.5 | 0.8 | 0.62 |  |  | 1.55 | 2.35 |  |  | 1
3.1.2 | Stairs
|  | 1 | 6 | 1.5 | 0.2 | 1.8 | [5 empty] | 0.2
|  | 2 | 2 | 0.7 | 0.2 | 0.28
|  | 3 | 2 | 0.7 | 0.2 | 0.28
3.1.3 | Walkway |  | 87.77 | 0.6 | 0.15 | 7.9 | [5 empty] | 0.15
3.1.4 | Ramp | 1 | 5 | 0.9 | 0.2 | 0.9
3.1.5 | Flowers Pot | F | 1.6 | 0.74 | 0.2 | 0.24
|  | SS | 1.4 | 0.54 | 0.2 | 0.15
| Stone Masonry in Foundation |  |  |  | Total | 108.56 | m3
3.2 | Stone work in Super structure | [8 empty] | Center to center length of the axes
3.2.1 | Stone Masonry along Axes | [7 empty] | Consd L | L | W | H | Length Add/Sub
| Main Axes | A | 22.75 | 0.6 | 0.25 | 3.41 |  |  | 22.75 | 22.4 | 0.8 | 0.25 | 1
|  | B | 22.75 | 0.6 | 0.25 | 3.41 |  |  | 22.75 | 22.4 | 0.6 |  | 1
|  | C | 29.75 | 0.6 | 0.25 | 4.46 |  |  | 29.75 | 29.4 | 0.35 |  | 1
|  | D | 29.75 | 0.6 | 0.25 | 4.46 |  |  | 29.75 | 29.4 |  |  | 1
|  | 1 | 3.85 | 0.6 | 0.25 | 0.58 |  |  | 3.85 | 4.65 |  |  | 1
|  | 2 | 5.6 | 0.6 | 0.25 | 0.84 |  |  | 5.6 | 7 |  | 1 | 1
|  | 3 | 3.85 | 0.6 | 0.25 | 0.58 |  |  | 3.85 | 4.65 |  |  | 1
|  | 4 | 3.85 | 0.6 | 0.25 | 0.58 |  |  | 3.85 | 4.65 |  |  | 1
|  | 5 | 3.85 | 0.6 | 0.25 | 0.58 |  |  | 3.85 | 4.65 |  |  | 1
|  | 6 | 4.25 | 0.6 | 0.25 | 0.64 |  |  | 4.25 |  |  |  | 1
|  | 7 | 3.85 | 0.6 | 0.25 | 0.58 |  |  | 3.85 | 4.65 |  |  | 1
|  | 8 | 3.85 | 0.6 | 0.25 | 0.58 |  |  | 3.85 | 4.65 |  |  | 1
|  | 9 | 5.6 | 0.6 | 0.25 | 0.84 |  |  | 5.6 | 7 |  | 1 | 1
|  | 10 | 3.85 | 0.6 | 0.25 | 0.58 |  |  | 3.85 | 4.65 |  |  | 1
| Second Axes | 1 | 1.95 | 0.5 | 0.25 | 0.24 |  |  | 1.95 | 2.55 | 0.5 |  | 1
|  | 2 | 1.75 | 0.5 | 0.25 | 0.22 |  |  | 1.75 | 2.35 |  |  | 1
|  | 3 | 1.75 | 0.5 | 0.25 | 0.22 |  |  | 1.75 | 2.35 |  |  | 1
3.2.2 | Stairs
|  | 1 | 6 | 1.1 | 0.15 | 0.99 | [5 empty] | 0.15
|  |  | 5.7 | 0.8 | 0.15 | 0.68
|  |  | 5.4 | 0.5 | 0.15 | 0.41
|  | 2 | 2 | 0.6 | 0.15 | 0.18 | [5 empty] | 0.15
|  |  | 2 | 0.3 | 0.15 | 0.09
|  | 3 | 2 | 0.6 | 0.15 | 0.18
|  |  | 2 | 0.3 | 0.15 | 0.09
3.2.3 | Sidewalk |  | 0 | 0.6 | 0.15 | 0
3.2.4 | Ramp | 1 | 4.16 | 0.9 | 0.25 | 0.94
| Stone Masonry in superstructure |  |  |  | Total | 26.51 | m3
4 | Pointing of Stone Masonry
4.1 | Plinth |  | 69.05 |  | 0.25 | 17.26 | m2
4.2 | Ramp |  | 4.16 |  | 0.25 | 1.04 | m2
| Pointing of Stone Masonry |  |  |  |  | 18.3 | m2
5 | RCC Work | [8 empty] | Center to center length of the axes
5.1 | RCC Ring Beams on Top of Stone Masonry | [7 empty] | Consd L | L | W | H | Length Add/Sub
| Main Axes | A | 22.75 | 0.35 | 0.3 | 2.39 |  |  | 22.75 | 22.4 | 0.35 | 0.3 | 1
|  | B | 22.75 | 0.35 | 0.3 | 2.39 |  |  | 22.75 | 22.4 |  |  | 1
|  | C | 29.75 | 0.35 | 0.3 | 3.12 |  |  | 29.75 | 29.4 |  |  | 1
|  | D | 29.75 | 0.35 | 0.3 | 3.12 |  |  | 29.75 | 29.4 |  |  | 1
|  | 1 | 4.3 | 0.35 | 0.3 | 0.45 |  |  | 4.3 | 4.65 |  |  | 1
|  | 2 | 6.3 | 0.35 | 0.3 | 0.66 |  |  | 6.3 | 7 |  |  | 2
|  | 3 | 4.3 | 0.35 | 0.3 | 0.45 |  |  | 4.3 | 4.65 |  |  | 1
|  | 4 | 4.3 | 0.35 | 0.3 | 0.45 |  |  | 4.3 | 4.65 |  |  | 1
|  | 5 | 4.3 | 0.35 | 0.3 | 0.45 |  |  | 4.3 | 4.65 |  |  | 1
|  | 6 | 4.7 | 0.35 | 0.3 | 0.49 |  |  | 4.7 |  |  |  | 1
|  | 7 | 4.3 | 0.35 | 0.3 | 0.45 |  |  | 4.3 | 4.65 |  |  | 1
|  | 8 | 4.3 | 0.35 | 0.3 | 0.45 |  |  | 4.3 | 4.65 |  |  | 1
|  | 9 | 6.3 | 0.35 | 0.3 | 0.66 |  |  | 6.3 | 7 |  |  | 2
|  | 10 | 4.3 | 0.35 | 0.3 | 0.45 |  |  | 4.3 | 4.65 |  |  | 1
| Secondary Axes | 1 | 0 | 0.35 | 0.3 | 0 |  |  | 0 | 0 |  |  | 0
|  | 2 | 0 | 0.35 | 0.3 | 0 |  |  | 0 | 0 |  |  | 0
|  | 3 | 0 | 0.35 | 0.3 | 0 |  |  | 0 | 0 |  |  | 0
| RCC Ring Beams on Stone Masonry |  |  |  | Total | 15.98 | m3
Center to center length of the axes
5.2 | RCC Drop Beam | [7 empty] | Consd L | L | W | H | Length Add/Sub
| Main Axes | A | 22.75 | 0.35 | 0.21 | 1.67 |  |  | 22.75 | 22.4 | 0.35 | 0.21 | 1
|  | B | 22.75 | 0.35 | 0.21 | 1.67 |  |  | 22.75 | 22.4 |  |  | 1
|  | C | 29.75 | 0.35 | 0.21 | 2.19 |  |  | 29.75 | 29.4 |  |  | 1
|  | D | 29.75 | 0.35 | 0.21 | 2.19 |  |  | 29.75 | 29.4 |  |  | 1
|  | 1 | 4.3 | 0.35 | 0.21 | 0.32 |  |  | 4.3 | 4.65 |  |  | 1
|  | 2 | 6.3 | 0.35 | 0.21 | 0.46 |  |  | 6.3 | 7 |  |  | 2
|  | 3 | 4.3 | 0.35 | 0.21 | 0.32 |  |  | 4.3 | 4.65 |  |  | 1
|  | 4 | 6.3 | 0.35 | 0.21 | 0.46 |  |  | 6.3 | 7 |  |  | 2
|  | 5 | 4.3 | 0.35 | 0.21 | 0.32 |  |  | 4.3 | 4.65 |  |  | 1
|  | 6 | 4.7 | 0.35 | 0.21 | 0.35 |  |  | 4.7 |  |  |  | 1
|  | 7 | 6.3 | 0.35 | 0.21 | 0.46 |  |  | 6.3 | 7 |  |  | 2
|  | 8 | 4.3 | 0.35 | 0.21 | 0.32 |  |  | 4.3 | 4.65 |  |  | 1
|  | 9 | 6.3 | 0.35 | 0.21 | 0.46 |  |  | 6.3 | 7 |  |  | 2
|  | 10 | 4.3 | 0.35 | 0.21 | 0.32 |  |  | 4.3 | 4.65 |  |  | 1
| Secondary Axes | 1 | 0 | 0.35 | 0.21 | 0 |  |  | 0 | 0 |  |  | 0
|  | 2 | 0 | 0.35 | 0.21 | 0 |  |  | 0 | 0 |  |  | 0
|  | 3 | 0 | 0.35 | 0.21 | 0 |  |  | 0 | 0 |  |  | 0
| RCC Drop Beams |  |  |  | Total | 11.51 | m3
5.3 | RCC Slabs
| Slab 1 | A | 30.95 | 6.2 | 0.14 | 26.86
| Salb 2 | B | 23.95 | 7 | 0.14 | 23.47
| RCC Slabs |  |  |  | Total | 50.33 | m3
5.4 | RCC Parapet
|  | A | 29.95 | 0.1 | 0.36 | 1.08
|  | B | 12 | 0.1 | 0.36 | 0.43
|  | C | 7 | 0.1 | 0.36 | 0.25
|  | D | 13.6 | 0.1 | 0.36 | 0.49
|  | E | 23.95 | 0.1 | 0.36 | 0.86
| RCC Parapet |  |  |  | Total | 3.11 | m3
| Total RCC |  |  |  | G.Total | 80.93 | m3
Center to center length of the axes
6 | Filling of floor with soil |  |  |  |  | Nos |  |  | Consd L | L | W | H | Length Add/Sub
|  | A | 7 | 4.3 | 0.31 | 6 | 55.99 | m3 | 29.05 | 29.4 | 0.35 | 0.35 | 1 | A | 6.55 | 3.85 | 0.35 | 8.83 | m3
|  | B | 4.8 | 4.3 | 0.31 | 1 | 6.4 | m3 | 22.75 | 22.4 |  |  | 1 |  | 21.68 | 0.23 | 0.1 | 0.5 | m3
|  | C | 22.75 | 2 | 0.35 | 1 | 15.93 |  | 29.75 | 29.4 |  |  | 1 | A
|  | D | 5.65 | 2.4 | 0.35 | 1 | 4.75 |  | 29.75 | 29.4 |  |  | 1
[9 empty] | 4.3 | 4.65 |  |  | 1
| Filling with Soil |  |  |  | Total | 83.07 | m3 |  | 6.3 | 7 |  |  | 2
[9 empty] | 4.3 | 4.65 |  |  | 1
[9 empty] | 6.3 | 7 |  |  | 2
7 | Boulders | [7 empty] | 4.3 | 4.65 |  |  | 1
|  | A | 7 | 4.3 | 0.15 | 6 | 27.09 | m3 | 4.7 |  |  |  | 1
|  | B | 4.8 | 4.3 | 0.15 | 1 | 3.1 | m3 | 6.3 | 7 |  |  | 2
|  | C | 22.75 | 2 | 0.15 | 1 | 6.83 |  | 4.3 | 4.65 |  |  | 1
|  | D | 5.65 | 2.4 | 0.15 | 1 | 2.03 |  | 6.3 | 7 |  |  | 2
[9 empty] | 4.3 | 4.65 |  |  | 1
[5 empty] | Total | 39.05 | m3 |  | 0 | 0 |  |  | 0
[9 empty] | 0 | 0 |  |  | 0
9 | PCC Work | [7 empty] | 0 | 0 |  |  | 0
9.1 | Floor | A | 7 | 4.3 | 0.1 | 6 | 18.06
|  | B | 4.8 | 4.3 | 0.1 | 1 | 2.06
|  | C | 22.75 | 2 | 0.1 | 1 | 4.55
|  | D | 5.65 | 2.8 | 0.1 | 1 | 1.58
[7 empty] | 26.25 | m3
9.2 | Stairs | 1 | 2 | 1.2 | 0.13 | 2 | 0.62
|  | 2 | 5.5 | 1.5 | 0.13 | 1 | 1.07
[7 empty] | 1.69 | m3
9.3 | Sidewalk | 1 | 87.77 | 0.6 | 0.1 | 1 | 5.27
|  | 2 | 87.77 | 0.2 | 0.05 | 1 | 0.88
[7 empty] | 6.15 | m3
9.4 | Ramp | 1 | 5 | 0.8 | 0.1 | 1 | 0.4 | m3
[9 empty] | Slabs | Length | Width | Parapet t
9.5 | Roof | A | 30.75 | 6 | 0.07 | 1 | 12.92 |  |  | 30.95 | 6.2 | 0.1
|  | B | 23.75 | 7 | 0.07 | 1 | 11.64 |  |  | 23.95 | 7
[7 empty] | 24.56 | m3
|  | A | 30.75 | 6 | 0.05 | 1 | 9.23
|  | B | 23.75 | 7 | 0.05 | 1 | 8.31
[7 empty] | 0 | m3
9.5 | Under the Windows | W1 | 1.24 | 0.44 | 0.05 | 19 | 0.52
|  | W2 | 0.74 | 0.44 | 0.05 | 7 | 0.11
|  | W3 | 1.74 | 0.44 | 0.05 | 1 | 0.04
[7 empty] | 0.67 | m3
9.6 | Flowers Pot | Bed | 1.45 | 0.6 | 0.15 | 1 | 0.13
|  | walls | 3.5 | 0.4 | 0.15 | 1 | 0.21
[7 empty] | 0.34 | m3
| PCC Total | [5 empty] | 60.06 | m3
10 | Isogam
10.1 | Floor | A | 7 | 4.3 |  | 6 | 180.6
|  | B | 4.8 | 4.3 |  | 1 | 20.64
|  | C | 22.75 | 2 |  | 1 | 45.5
|  | D | 5.65 | 2.8 |  | 1 | 15.82
[7 empty] | 262.56 | m3
10.2 | Roof | A | 30.75 | 6 |  | 1 | 184.5
|  | B | 23.75 | 7 |  | 1 | 166.25
[7 empty] | 350.75 | m3
| Isogam Total | [5 empty] | 613.31 | m2
11 | Burnt Brick Pieces
11.1 | Roof | A | 30.75 | 6 | 0.1 | 1 | 18.45
|  | B | 23.75 | 7 | 0.1 | 1 | 16.63
| Burnt Brick Pieces Total | [5 empty] | 35.08 | m3
12 | Brick Work | [8 empty] | Center to center length of the axes
12.1 | Walls | [7 empty] | Consd L | L | W | H | Length Add/Sub
| Main Axes | A | 22.75 | 0.35 | 2.64 | 21.02 |  |  | 22.75 | 22.4 | 0.35 | 2.64 | 1
|  | B | 22.75 | 0.35 | 2.64 | 21.02 |  |  | 22.75 | 22.4 |  |  | 1
|  | C | 29.75 | 0.35 | 2.64 | 27.49 |  |  | 29.75 | 29.4 |  |  | 1
|  | D | 29.75 | 0.35 | 2.64 | 27.49 |  |  | 29.75 | 29.4 |  |  | 1
|  | 1 | 4.3 | 0.35 | 2.64 | 3.97 |  |  | 4.3 | 4.65 |  |  | 1
|  | 2 | 6.3 | 0.35 | 2.64 | 5.82 |  |  | 6.3 | 7 |  |  | 2
|  | 3 | 4.3 | 0.35 | 2.64 | 3.97 |  |  | 4.3 | 4.65 |  |  | 1
|  | 4 | 4.3 | 0.35 | 2.64 | 3.97 |  |  | 4.3 | 4.65 |  |  | 1
|  | 5 | 4.3 | 0.35 | 2.64 | 3.97 |  |  | 4.3 | 4.65 |  |  | 1
|  | 6 | 4.7 | 0.35 | 2.64 | 4.34 |  |  | 4.7 |  |  |  | 1
|  | 7 | 4.3 | 0.35 | 2.64 | 3.97 |  |  | 4.3 | 4.65 |  |  | 1
|  | 8 | 4.3 | 0.35 | 2.64 | 3.97 |  |  | 4.3 | 4.65 |  |  | 1
|  | 9 | 6.3 | 0.35 | 2.64 | 5.82 |  |  | 6.3 | 7 |  |  | 2
|  | 10 | 4.3 | 0.35 | 2.64 | 3.97 |  |  | 4.3 | 4.65 |  |  | 1
| Secondary Axes | 1 | 0 | 0.35 | 2.64 | 0 |  |  | 0 | 0 |  |  | 0
|  | 2 | 0 | 0.35 | 2.64 | 0 |  |  | 0 | 0 |  |  | 0
|  | 3 | 0 | 0.35 | 2.64 | 0 |  |  | 0 | 0 |  |  | 0
[5 empty] | Sub.Total | 140.79 | m3
| Brick work Total |  |  |  | Total | 110.38 | m3
Nos
13 | Making of windows | W1 | 1.7 | 1.2 | 19 |  | 38.76
|  | W2 | 1.2 | 0.7 | 7 |  | 5.88
|  | W3 | 2 | 1.7 | 1 |  | 3.4
| Making of Windows Total | [5 empty] | 48.04 | m2
14 | Making of Doors
|  | D1 | 1 | 2.54 | 7 |  | 17.78
|  | D2 | 1.8 | 2.75 | 2 |  | 9.9
|  | DW | 2.2 | 2.54 | 2 |  | 11.176 | m2
[7 empty] | 38.86 | m2
15 | Plaster
15.1 | Interior |  |  |  |  | Nos
15.1.1 | walls | R1 | 7 | 4.3 | 2.75 | 6 | 372.9 |  | Doors and windows not subtracted
|  | R2 | 17.3 |  | 2.75 | 1 | 47.58 |  | Doors and windows not subtracted
|  | C1 | 22.75 |  | 2.75 | 2 | 97.56 |  | Doors and windows subtracted
|  | C2 | 3 |  | 2.75 | 2 | 16.5
[7 empty] | 536.54 | m2
15.1.2 | Ceiling | R1 | 7 | 4.3 |  | 6 | 180.6
|  | R2 | 4.8 | 4.3 |  | 1 | 20.64
|  | C1 | 22.75 | 2 |  | 1 | 45.5
|  | C2 | 3 | 2.2 |  | 1 | 6.6
[7 empty] | 255.34 | m2
| Interior Plaster Total | [5 empty] | 791.88 | m2
15.2 | Exterior
15.2.1 | Walls | W1 | 29.75 |  | 3.15 | 1 | 69.23
|  | W2 | 5 |  | 3.15 | 2 | 31.5
|  | W3 | 5.3 |  | 3.15 | 2 | 31.71
|  | W4 | 1.8 |  | 2.75 | 2 | 9.9
|  | W5 | 7 |  | 3.15 | 2 | 44.1
|  | W6 | 11.15 |  | 3.15 | 1 | 25.6
|  | W7 | 4.2 |  | 2.75 | 1 | 11.55
|  | W8 | 7 |  | 3.15 | 1 | 15.93
[7 empty] | 239.52 | m2
15.2.2 | Parapet
|  | H1 | 30.95 | 0.6 |  | 1 | 18.57
|  | H2 | 5 | 0.6 |  | 2 | 6
|  | H3 | 3.45 | 0.6 |  | 2 | 4.14
|  | H4 | 6.4 | 0.6 |  | 2 | 7.68
|  | H5 | 23.95 | 0.6 |  | 1 | 14.37
|  | W1 | 30.95 |  | 0.9 | 1 | 27.86
|  | W2 | 5 |  | 0.9 | 2 | 9
|  | W3 | 3.45 |  | 0.9 | 2 | 6.21
|  | w4 | 6.4 |  | 0.9 | 2 | 11.52
|  | w5 | 23.95 |  | 0.9 | 1 | 21.56
[7 empty] | 126.91 | m2
| Exterior Plaster Total | [5 empty] | 366.43 | m2
16 | White Washing of Inerior walls and Ceiling | [5 empty] | 791.88 | m2
17 | White Washing of Outside Walls and Parapet | [5 empty] | 366.43 | m2
18 | Making of Blackboards | BB | 2.4 | 1.2 |  | 6 | 17.28 | m2
19 | Making of Wooden frame for Blackboard | BBF | 2.4 | 1.2 |  | 6 | 34.56 | LM
20 | Chimney Cover | CC |  |  |  | 7 | 7 | Nos
Making of Chimney with all its Necessary work (Removable Concrete Cover with GI Sheet, Concrete Pipe, Brick work, Chimney Cup) as per drawings
21 | Gutters work (Vertical from GI sheet 24 gage 12X20 cm) |  |  |  |  | 18 | 18 | LM | In Original BOQ
| Drain Spout Guage 22 (15x20cm) |  |  |  | 3.75 | 5 | 18.75 | LM | In drawings
22 | Making of Handrails | HR |  |  |  | 8 | 8 | LM
23 | Iron Sheet 24 Gauge for parapet wall
|  | H1 | 31.05 | 0.2 |  | 1 | 6.21
|  | H2 | 6.3 | 0.2 |  | 2 | 2.52
|  | H3 | 3.5 | 0.2 |  | 2 | 1.4
|  | H4 | 7.7 | 0.2 |  | 2 | 3.08
|  | H5 | 23.95 | 0.2 |  | 1 | 4.79
[7 empty] | 18 | m2
24 | Cleaning of area from Extra material and shift to the fair pleace with all Necessary Requirements | [5 empty] | 400 | m2
Marble
|  | W1 | 1.7 | 0.45 | 19 |  | 14.535 | m2
|  | W2 | 1.2 | 0.45 | 7 |  | 3.78 | m2

## Summary of BOQ (hidden)
6 Class Room Burnt Brick Wall RCC Roof School, H=2.75m
(A) Building Work
Item | Description | Unit | New Quantity | Remarks
1 | Site Preparation | LS | 1 | Shall be considered as LS but in the in the original BOQ its in the Sqm of the Building
2 | Excavation of foundation and pavements in Grad 3 land and all necessary Requirment. | m3 | 136.38
3 | Back Filling of Foundation | m3 | 28.34 | Back Filling is New Item its not in the Origional BOQ
4 | Stone Masonry of foundation with 1:4 mortar and all necessary Requirment. | m3 | 108.56
5 | Super stone Masonry with1:4 mortar and all necessary Requirment. | m3 | 26.51
6 | Pointing of stone work with 1:3 cement mortar and all necessary work | m2 | 18.3
7 | R.C.C (1:1.5:3) of rings, beams, slabs and parapet according to drawing with all necessary Requirment. | m3 | 80.93 | In the original BOQ they did not mentioned the slabs and parapet in the BOQ description | R.C.C (1:1.5:3) of rings on the top of Super stone Masonry and wall according to drawing with all necessary Requirment.
8 | Filling of floor with soil including compaction (thick=35cm) and all Necessary Requirment. | m3 | 83.07 | In th Drawings the thickness is given 37 cm
9 | Filling of floor and sidewalks with boulders including compaction (thick = 15cm) with all necessary Requirment. | m3 | 39.05
10 | P.C.C (1:2:4) of floor , stairs , sidewalk, roof according to the drawing with all necessary Requirment. | m3 | 60.06 | In drawings it seems that the PCC on the Burnt brick pieces at roof is recommended 7 cm but in the design its 5 cm
11 | Brick masonry of walls (w = 35cm) and roof with 1:4 cement-sand mortar with all Necessary Requirment. | m3 | 110.38 | Brick Pieces on the roof shall be seperated from Brick masonry work
12 | Burnt Brick Pieces on Roof with all Necessary Requirment. | m3 | 35.08 | New item. This is combined with the Brick masonry work in Original BOQ but I split them as it is technically not correct because its easy to work and it does not require morter
13 | Plaster of interior walls and ceilings including cleaning with 1:3 cement - sand mortar and all necessary Requirment | m2 | 791.88
14 | Plaster of Out Side walls and parapet including cleaning with 1:3 cement - sand mortar and all necessary Requirment | m2 | 366.43
15 | White washing of interior walls and ceilings (3 Coat) with 75% emulsion with all necessary Requirements | m2 | 791.88
16 | White washing of out side walls (3 Coat) with 100% emulsion with all necessary Requirements | m2 | 366.43
17 | Making of complate Windows and instalation with all necessary work (frame, glass, oil paint) high quality. | m2 | 48.04
18 | Making of complate doors and instalation with all necessary work (frame, glass, oil paint) high quality. | m2 | 38.86
19 | Making of blackboard with cement mortar (1:3) with special paint | m2 | 17.28
20 | Macking wooden frame for blackboard with all necessary work | LM | 34.56
21 | Isogam for roofing with all necessary work | m2 | 613.31
22 | Chimney Cover with all necessary work | Nos | 7 | the Description shall be changed to (Making of Chimney with all its Necessary work (Removable Concrete Cover with GI Sheet, Concrete Pipe, Brick work, Chimney Cup) as per drawings)
23 | Gutters work (Vertical from GI sheet 24 gage 12X20 cm) with all necessary work . | LM | 18.75 | In drawings it is shown as Drain Spout Guage 22 (15x20cm) and also the unit is sqm in BOQ but it has to be LM
24 | Making of Handrails | LM | 8
25 | Iron Sheet 24 Gauge for parapet wall | m2 | 18
26 | Cleaning of area from Extra material and shift to the fair pleace with all Necessary Requirements | m2 | 400 | This is the same as the site preparation and It is recommended to be removed
27 | Marble |  | 18.5
28 | Preparation and Instalation of Signboard | LS | 1 | New Item

## Comparison (hidden)
6 Class Room Burnt Brick Wall RCC Roof School, H=2.75m
(A) Building Work
Item | Description | Unit | New Quantity | Old Quantity | Remarks
1 | Site Preparation | m2 | 1 | 474.51 | Shall be considered as LS but in the in the original BOQ its in the Sqm of the Building
2 | Excavation of foundation and pavements in Grad 3 land and all necessary Requirment. | m3 | 136.38 | 120.96
3 | Back Filling of Foundation | m3 | 28.34 | 0 | Back Filling is New Item its not in the Origional BOQ
4 | Stone Masonry of foundation with 1:4 mortar and all necessary Requirment. | m3 | 108.56 | 99.24
5 | Super stone Masonry with1:4 mortar and all necessary Requirment. | m3 | 26.51 | 23.21
6 | Pointing of stone work with 1:3 cement mortar and all necessary work | m2 | 18.3 | 14.94
7 | R.C.C (1:1.5:3) of rings, beams, slabs and parapet according to drawing with all necessary Requirment. | m3 | 80.93 | 81.42 | In the original BOQ they did not mentioned the slabs and parapet in the BOQ description
8 | Filling of floor with soil including compaction (thick=35cm) and all Necessary Requirment. | m3 | 83.07 | 70.68 | In th Drawings the thickness is given 37 cm
9 | Filling of floor and sidewalks with boulders including compaction (thick = 15cm) with all necessary Requirment. | m3 | 39.05 | 47.76
10 | P.C.C (1:2:4) of floor , stairs , sidewalk, roof according to the drawing with all necessary Requirment. | m3 | 60.06 | 85.8 | In drawings it seems that the PCC on the Burnt brick pieces at roof is recommended 7 cm but in the design its 5 cm
11 | Brick masonry of walls (w = 35cm) and roof with 1:4 cement-sand mortar with all Necessary Requirment. | m3 | 110.38 | 144.1 | Brick Pieces on the roof shall be seperated from Brick masonry work
12 | Burnt Brick Pieces on Roof with all Necessary Requirment. | m3 | 35.08 | 0 | New item. This is combined with the Brick masonry work in Original BOQ but I split them as it is technically not correct because its easy to work and it does not require morter
12 | Plaster of interior walls and ceilings including cleaning with 1:3 cement - sand mortar and all necessary Requirment | m2 | 791.88 | 873.3
13 | Plaster of Out Side walls and parapet including cleaning with 1:3 cement - sand mortar and all necessary Requirment | m2 | 366.43 | 327.84
14 | White washing of interior walls and ceilings (3 Coat) with 75% emulsion with all necessary Requirements | m2 | 791.88 | 873.3
15 | White washing of out side walls (3 Coat) with 100% emulsion with all necessary Requirements | m2 | 366.43 | 327.84
16 | Making of complate windows and instalation with all necessary work (frame, glass, oil paint) high quality. | m2 | 48.04 | 47.92
17 | Making of complate doors and instalation with all necessary work (frame, glass, oil paint) high quality. | m2 | 38.86 | 40.74
18 | Making of blackboard with cement mortar (1:3) with special paint | m2 | 17.28 | 17.28
19 | Making of wooden frame for blackboard with all necessary work | LM | 34.56 | 43.2
20 | Isogam for roofing with all necessary work | m2 | 613.31 | 644.21
21 | Chimney Cover with all necessary work . | Nos | 7 | 6 | the Description shall be changed to (Making of Chimney with all its Necessary work (Removable Concrete Cover with GI Sheet, Concrete Pipe, Brick work, Chimney Cup) as per drawings)
22 | Gutters work (Vertical from GI sheet 24 gage 12X20 cm) with all necessary work . | m2 | 18.75 | 18 | In drawings it is shown as Drain Spout Guage 22 (15x20cm) and also the unit is sqm in BOQ but it has to be LM
23 | Making of Handrails | LM | 8 | 8
24 | Iron Sheet 24 Gauge for parapet wall | m2 | 18 | 20.92
25 | Cleaning of area from Extra material and shift to the fair pleace with all Necessary Requirements | m2 | 400 | 400 | This is the same as the site preparation and It is recommended to be removed
26 | Prparation and Instalation of Signbaord | LS | 1 |  | New Item
27 | Preparation and Instalation of Signboard | LS | 1

## Construction of 6+1 Classrooms
Construction of 6+1 Classrooms
S.No | Description | Unit | Quantity | Unit Rate (AFN) | Total (AFN)
A-Civil Works
A.0 | Sign Board
Note: Supply and install project signboards made from metallic 200X100 cm, design of signboard shall be approved by UNICEF
A.0.a | Sign board | No | 1
A.1 | Site preparation
Note: Site preparation this include site leveling (excavation or backfilling) removing any trees, vegetation, debris, or other obstructions from the construction site as per specification and engineers directions with all required activities.
A.1.a | Building Area | m2 | 400
A.2 | Excavation
Note: Excavation of all types of lands for foundation, Stairs, Walkway and Ramp as per design drawings and specifications with all required activities
A.2.a | Foundation | m3 | 120.31
A.2.b | Stairs | m3 | 3
A.2.c | Walkway | m3 | 12
A.2.d | Ramp | m3 | 1
A.3 | Stone masonry
Note: Stone masonry in foundations and above foundation, with M1:4 as per design drawings, specification and engineers’ directions with all required activities
A.3.a | Foundation | m3 | 97
A.3.b | Stairs | m3 | 2.5
A.3.c | Walkway | m3 | 8
A.3.d | Ramp | m3 | 1
A.3.e | Flowers Pot | m3 | 0.5
A.3.f | Stone Masonry above foundation | m3 | 26.5
A.4 | Back filling
Note: filling with soil including levelling and compaction of building floor as per design drawings, specification, and engineer directions with all required activities.
A.4.a | Back filling Foundation | m3 | 24
A.4.b | Back filling Stairs | m3 | 0.5
A.4.c | Back filling Walkway | m3 | 3.5
A.4.d | Back Filling Ramp | m3 | 0.5
A.4.e | Buliding floor | m3 | 83
A.5 | Boulders
Note: Boulders placing with compaction for building floor and sidewalks with thickness of 15 cm as per design drawings, specification, and engineer directions with all required activities.
A.5.a | Inside of Building and walkway | m3 | 40
A.6 | PCC (M150)
Note: PCC (M150) with formworks as per design drawings, specification and engineers’ directions with all required activities
A.6.a | Floor | m3 | 36.75
A.6.b | Stairs | m3 | 1.69
A.6.c | Walkway | m3 | 6.15
A.6.d | Ramp | m3 | 0.4
A.6.e | Roof | m3 | 42.09
A.6.f | Windows sill (bottom) | m3 | 0.67
A.6.g | Flowers Pot | m3 | 0.34
A.7 | RCC (M250)
Note: RCC (M250) with form works as per design drawings, specification and engineers’ directions with all required activities
A.7.a | Ring Beam | m3 | 16
A.7.b | Drope Beams | m3 | 11.5
A.7.c | Slabs | m3 | 50
A.7.d | Parapet | m3 | 3
A.8 | Burnt brick masonry
Note: Burnt brick masonry with M1:4 as per design drawings, specification and engineers’ directions with all required activities
A.8.a | Walls | m3 | 110
A.9 | Burnt brick pieces
Note: Burnt brick pieces for insulation as per design drawings, specification and engineers’ directions with all required activities
A.9.a | Roof | m3 | 35
A.10 | Construction of blackboard
Note: Construction of blackboard with cement mortar along with special paint application as per design drawings, specification and engineers’ directions with all required activities
A.10.a | Blackboard | m2 | 17
Total of A- Civil Works
B Finishing
B.1 | Supply and installation of wooden windows
Note:Supply and installation of wooden windows, including accessories, and aluminum fly screens, 4mm Glasses as per design drawings, specification and engineers’ directions with all required activities
B.1.a | Windows 1 | m2 | 39
B.1.b | Windows 2 | m2 | 6
B.1.c | Windows 3 | m2 | 3.5
B.2 | Supply and installation of wooden doors
Note: Supply and installation of wooden doors, including accessories, Glasses as per design drawings, specification and engineers’ directions with all required activities
B.2.a | Door 1 | m2 | 18
B.2.b | Door 2 | m2 | 10
B.2.c | Door 3 | m2 | 11
B.3 | Interior cement plaster
Note: Interior cement plaster for walls and ceilings with M1:3 as per design drawings, specification and engineers’ directions with all required activities
B.3.a | Walls | m2 | 536.5
B.3.b | Ceiling | m2 | 255
B.4 | Exterior cement plaster
Note: Exterior cement plaster for walls and parapets with M1:3 as per design drawings, specification and engineers’ directions with all required activities
B.4.a | Walls | m2 | 239.5
B.4.b | Parapet | m2 | 127
B.5 | Marbal
Note: Afghan white marble for windows sill (bottom) with 2.5cm thickness as per design drawings, specification and engineers’ directions with all required activities
B.5.a | Windows1 | m2 | 14.5
B.5.b | Windows2 | m2 | 4
B.6 | Stone pointing
Note: Stone masonry (beaded pointing) with M1:3 as per design drawings, specification and engineers’ directions with all required activities
B.6.a | Plinth | m2 | 17.5
B.6.b | Ramp | m2 | 1
B.7 | Wooden frame installation for blackboard
Note: Wooden frame installation for blackboard as per design drawings, specification and engineers’ directions with all required activities.
B.7.a | Wooden Frame for black board | Lm | 34.5
B.8 | construction of chimney
Note: Complete construction of chimney, concrete pipe, brickworks, chimney cap, precast concrete chimney cover and GI sheet as per design drawings, specification and engineers’ directions with all required activities.
B.8.a | Chimney | No | 7
B.9 | Vertical roof gutters
Note: Vertical roof gutters from GI sheet 22 gauge 12x20 cm as per design drawings, specification and engineers’ directions with all required activities.
B.9.a | Gutters work (Vertical from GI sheet 24 gage 12X20 cm) | Lm | 19
B.10 | Interior latex wall and ceilling painting
Note: Interior latex wall and ceilling painting 75 % (3 coat) with plaster texture filling as per design drawings, specification and engineers’ directions with all required activities
B.10 | Walls | m2 | 536.5
B.10.a | Ceiling | m2 | 255.5
B.11 | Isogum (Waterproofing)
Note: Isogum (Waterproofing) 5mm thick as per design drawings, specification and engineers’ directions with all required activities.
B.11.a | Floor | m2 | 262.5
B.11.b | Roof | m2 | 350.75
B.12 | Exterior latex wall and parapet painting
Note: Exterior latex wall and parapet painting 100 % (3 coat) with plaster texture filling as per design drawings, specification and engineers’ directions with all required activities
B.12.a | Walls | m2 | 239.5
B.12.b | Parapet | m2 | 127
B.13 | Handrails installation
Note: Handrails installation as per design drawings, specification and engineers’ directions with all required activities
B.13.a | Handrail | Lm | 8
B.14 | Covering parapet wall with 24 gauge GI
Note: Covering the top of the parapet wall with 24 gauge GI sheet as per design drawings, specification and engineers’ directions with all required activities.
B.14.a | Parapet | m2 | 18
Total of B- Finishing
C Electrical Works
C.1 | Lights
Note: LED surface mounting fixture 18 X 18 X 4 cm 25W 220V 50hz as per design drawings, specification and engineers’ directions with all required activities.
C.1.a | LED Lights | No | 33
C.2 | Double pole switches
Note: Double pole switches 10 Amps under plaster as per design drawings, specification and engineers’ directions with all required activities.
C.2.a | Double pole switches | No | 6
C.3 | Single pole switches
Note: Single pole switches 10 Amps under plaster as per design drawings, specification and engineers’ directions with all required activities.
C.3.a | Single pole switches 10 Amps | No | 6
C.4 | Socket 16 Amp
Note: Socket 16 Amp under plaster as per design drawings, specification and engineers’ directions with all required activities.
C.4.a | Socket 16 Amp | No | 25
C.5 | Copper Wire 1 X 2.5mm² for lighting
Note: Copper Wire 1 X 2.5mm² for lighting as per design drawings, specification and engineers’ directions with all required activities.
C.5.a | Copper Wire | Lm | 560
C.6 | Copper Wire 1 X 4mm² for power
Copper Wire 1 X 4mm² for lighting as per design drawings, specification and engineers’ directions with all required activities.
C.6.a | Copper Wire | Lm | 450
C.7 | PVC conduit 1" or 25mm
Note: PVC conduit 1" or 25mm including fittings as per design drawings, specification and engineers’ directions with all required activities.
C.7.a | PVC conduit | Lm | 350
C.8 | PVC conduit 3" or 75mm
Note:PVC conduit 3" or 75mm including fittings as per design drawings, specification and engineers’ directions with all required activities.
C.8.a | PVC conduit | Lm | 30
C.9 | Copper Cable 3 X25mm² or 2 X 25mm² + 1 X25mm²
Note: Copper Cable3 X25mm² or 2 X 25mm² + 1 X25mm² for lighting as per design drawings, specification and engineers’ directions with all required activities.
C.9.a | Copper Cable | Lm | 30
C.10 | Grounding rods (Cu) 2.5 m length 16mm diameter
Note: Grounding rods (Cu) 2.5 m length 16mm diameter as per design drawings, specification and engineers’ directions with all required activities.
C.10.a | Grounding Rod | Set | 1
C.11 | Circuit breaker 20 Amp
Note: Circuit breaker 20 Amp for power receptacle as per design drawings, specification and engineers’ directions with all required activities.
C.11.a | Circuit breaker | No | 8
C.12 | Circuit breaker 10 Amp
Note: Circuit breaker 10 Amp for lighting as per design drawings, specification and engineers’ directions with all required activities.
C.12.a | Circuit breaker | No | 8
C.13 | Distribution Box 30 x 45cm 22 gauge
Note: Distribution Box 30 x 45cm 22 gauge as per design drawings, specification and engineers’ directions with all required activities.
C.13.a | Distribution Box | No | 1
C.14 | MCB 63 Apms
Note: MCB 63 Apms for distribtion box Two port (Single Phase) as per design drawings, specification and engineers’ directions with all required activities.
C.14.a | MCB 63 Apms | No | 1
C.15 | Joint box
Note: Joint box as per design drawings, specification and engineers’ directions with all required activities.
C.15.a | Joint box | No | 15
C.16 | Insulation Tape
Note: Insulation Tape as per design drawings, specification and engineers’ directions with all required activities.
C.16.a | Insulation Tape | Roll | 10
C.17 | Single device gnag (Boxes)
Note: Single device gnag (Boxes) as per design drawings, specification and engineers’ directions with all required activities.
C.17.a | Single device gnag (Boxes) | No | 40
C.18 | 320 Watt Monocrystalline PhotoVoltaic (PV) Solar Modules -Module peak power at STC [W]= = 320; -25 years’ linear performance guarantee (90% up to 10 years); -Positive Power tolerance >= 3%; -Open circuit voltage Voc [V] =45.72; -Short-circuit current Isc [A] =9.28, -Voltage at max power Vmp [V] =36.75, -Current at max power Imp [A] =8.71, -Max System Voltage [V] = 1000. 1) The crystalline silicon panels should meet the minimum requirement of IEC-61215-2 / IEC-61730-1-2. 2) Crystalline modules shall be equipped with bypass diode(s) located in the PV module junction box. 3) Replacement of bypass diode shall be possible without replacing the module. 4) All modules shall be Class II (according IEC 60364-4-41) and the efficiency shall be greater than 18% at STC conditions. 5) The encapsulation shall withstand snow, rain, dust, and thermal fatigue and shall be abrasion resistant during the requested lifetime (25 years). 6) PV Array and PV Sub-array junction boxes exposed to the environment shall be at least IP 65 compliant in accordance with IEC 60529, and shall be UV resistant. | No | 20
C.19 | Advanced Solar Inverter + MPPT, with battery equalization function, supports LiFePO4 batteries, with battery use optional and built-in MPPT solar charger Paralleling option - up to 12 units • Rated Power: 6000W • Maximum PV Array Open Circuit Voltage: 1000Vdc • 1 Phase, AC Ouput • With in-built Charge Controller • Inverting DC to AC Simultanuousely charge the batteries and directly run the load during the sun hours. • Battery Voltage: 48Vdc • MPPT Solar Charge Current: 100A • Maximum PV Array Power: 6000W • Communication Interface: USB/RS232 1 Year Product Warranty 2 pcs connected in parallel: 11kW Warranty: 12 months (manufacturer) | No | 1
C.20 | 200 Ah Sealed Lead Acid, Maintenance-Free, Deep Cycle, GEL Batteries - Fast Charging Technology -Capacity: 200Ah@10hr-rate -Voltage per unit: 12Vdc -Maximum Discharge Current: 2000A (5 sec) -Operating Temperature Range: -20°C ~ 60°C -Warranty: 12 months (manufacturer) | No | 20
C.21 | Supply and Installation of high quality GI structure for mounting of SOLAR PANELS frame / structure, completing of works with all its included details. | set | 1
C.22 | Supply and installation of high quality Array Junction box with all accessories for outdoor usage with weather proof enclosure. -Each junction boxes shall be provided with suitable metal oxide varistors ( Mov's) / surge arresters, one fuse, one spd & one DC breaker per string. - Including Earthing/Grounding | No | 1
C.23 | Copper Conductor for connection of PV to Inverter Supply and installation of(2*6 mm2) Multi strand Annealed high conductivity copper conductor FRLS PVC insulated 1000 V rating flexible wires for D.C side in the existing PVC conduit | m | 200
C.24 | Copper Conductor for connection of Batteries with Inverter -conductor Size= 25mm2; -Voltage Rating: 100VDC; -conductor & battery clamps material= Copper with double insulation The clamps for battery connection should have precise dimensions to fit battery posts for maximum contact and have best balance of conductivity and durability. | m | 10
Total of C- Electrical
Summary
Total of A- Civil Works
Total of B- Finishing
Total of C- Electrical
Grand Total

## Construction of 4+1 Dry Latrine
Construction of 4 + 1 Dry Latrine
S.No | Description | Unit | Quantity | Unit Rate (AFN) | Total (AFN)
A-Civil Works
A.1 | Site preparation
Note: Site preparation this include site leveling (excavation or backfilling) removing any trees, vegetation, debris, or other obstructions from the construction site as per specification and engineers directions with all required activities.
A.1.a | Building Area | m2 | 87.5
A.2 | Excavation
Note: Excavation of all types of lands for foundation, Stairs, Walkway and Ramp as per design drawings and specifications with all required activities
A.2.a | Foundation | m3 | 23.5
A.2.b | Stairs | m3 | 0.5
A.2.c | Ramp | m3 | 7
A.2.d | Wastage | m3 | 5.7544
A.2.e | Walkway | m3 | 2.5
| Soak Pit | m3 | 1
A.3 | Stone masonry
Note: Stone masonry in foundations and above foundation, with M1:4 as per design drawings, specification and engineers’ directions with all required activities
A.3.a | Latrine foundation | m3 | 18.25
A.3.b | Stairs foundation | m3 | 0.4
A.3.c | Ramp foundation | m3 | 5
A.3.d | Wastage foundation | m3 | 4.5
A.3.e | Above latrine foundation | m3 | 19
A.3.f | Stone Masonry above foundation Ramp | m3 | 4
A.3.g | Stone Masonry above foundation Wastage | m3 | 4
A.4 | filling
Note: filling with soil including levelling and compaction of building floor as per design drawings, specification, and engineer directions with all required activities.
A.4.a | Back filling Foundation | m3 | 5.2
A.4.b | Back filling Stairs | m3 | 0.2
A.4.c | Back filling Ramp | m3 | 1.75
A.4.d | Back filling Wastage | m3 | 1.25
A.4.e | Back filling Walkway | m3 | 0.5
A.4.f | Corridor | m3 | 5.2
A.4.g | Stairs | m3 | 0.74694
A.4.h | Ramp | m3 | 4
A.5 | Boulders
Note: Boulders placing with compaction for building floor and sidewalks with thickness of 15 cm as per design drawings, specification, and engineer directions with all required activities.
A.5.a | Corridor | m3 | 1.2
A.5.b | Stairs | m3 | 0.6
A.5.c | Bottom of latrine | m3 | 0.6
A.5.d | Wastage | m3 | 1.25
A.5.e | Ramp | m3 | 1
A.5.f | Walkway | m3 | 2.5
A.6 | PCC (M150)
Note: PCC (M150) with formworks as per design drawings, specification and engineers’ directions with all required activities
A.6.a | Corridor | m3 | 1
A.6.b | Stairs | m3 | 0.5
A.6.c | Bottom of latrine | m3 | 0.5
A.6.d | Wastage | m3 | 1
A.6.e | Ramp | m3 | 1.5987
A.6.f | Walkway | m3 | 1.7
A.6.g | Top Slab | m3 | 3.5
A.7 | RCC (M250)
Note: RCC (M250) with form works as per design drawings, specification and engineers’ directions with all required activities
A.7.a | foundation Tie beam | m3 | 3
A.7.b | wastage foundation Tie beam | m3 | 0.8
A.7.c | Top Ring beam | m3 | 2.3
A.7.d | Top Slab | m3 | 5.7
A.7.e | Slab Parapet Wall | m3 | 1
A.7.f | Wastages slabs (1.6mx0.9m) | m3 | 1
A.7.g | Latrines slabs (4x1.5mx1m) (1x1.5mx1.5m) | m3 | 0.9
A.7.h | Soak Pit | m3 | 0.1
A.8 | Burnt brick masonry
Note: Burnt brick masonry with M1:4 as per design drawings, specification and engineers’ directions with all required activities
A.8.a | Walls | m3 | 23
A.9 | Burnt brick pieces
Note: Burnt brick pieces for insulation as per design drawings, specification and engineers’ directions with all required activities
A.9.a | Roof | m3 | 3.5
A.10 | Ventilation Pipe
Note: PVC 4" Pipe as per design drawings, specification and engineers’ directions with all required activities
A.10.a | Vent Pipe | Lm | 20
A.11 | Urine Channel
Note: GI 2" with T-joint as per design drawings, specification and engineers’ directions with all required activities
A.11.a | Urine Channel | Lm | 9.5
Total of A- Civil Works
B Finishing
B.1 | Supply and installation of wooden windows
Note:Supply and installation of wooden windows, including accessories, and aluminum fly screens, Glasses as per design drawings, specification and engineers’ directions with all required activities
B.1.a | Windows 1 | m2 | 1.5
B.1.b | Windows 2 | m2 | 0.8
B.1.c | Windows 3 | m2 | 1.8
B.2 | Supply and installation of wooden doors
Note: Supply and installation of wooden doors, including accessories as per design drawings Glasses, specification and engineers’ directions with all required activities
B.2.a | Door 1 | m2 | 6.7
B.2.b | Door 2 | m2 | 2.6
B.3 | Interior cement plaster
Note: Interior cement plaster for walls and ceilings with M1:3 as per design drawings, specification and engineers’ directions with all required activities
B.3.a | Walls | m2 | 116
B.3.b | Ceiling | m2 | 22.5
B.4 | Exterior cement plaster
Note: Exterior cement plaster for walls and parapets with M1:3 as per design drawings, specification and engineers’ directions with all required activities
B.4.a | Walls | m2 | 56.5
B.4.b | Parapet | m2 | 42
B.5 | Stone pointing
Note: Stone masonry (beaded pointing) with M1:3 as per design drawings, specification and engineers’ directions with all required activities
B.5.a | Latrine | m2 | 42
B.5.b | Wastage | m2 | 16.5
B.5.c | Ramp | m2 | 10
B.6 | Vertical roof gutters
Note: Vertical roof gutters from GI sheet 22 gauge 12x20 cm as per design drawings, specification and engineers’ directions with all required activities.
B.6.a | Gutters work (Vertical from GI sheet 24 gage 12X20 cm) | Lm | 8
B.7 | Interior latex wall and ceilling painting
Note: Interior latex wall and ceilling painting 75 % (3 coat) with plaster texture filling as per design drawings, specification and engineers’ directions with all required activities
B.7 | Walls | m2 | 116
B.7.a | Ceiling | m2 | 22.5
B.8 | Isogum (Waterproofing)
Note: Isogum (Waterproofing) 5mm thick as per design drawings, specification and engineers’ directions with all required activities.
B.8.a | Roof | m2 | 48
B.9 | Exterior latex wall and parapet painting
Note: Exterior latex wall and parapet painting 100 % (3 coat) with plaster texture filling as per design drawings, specification and engineers’ directions with all required activities
B.9.a | Walls | m2 | 56.5
B.9.b | Parapet | m2 | 42
B.10 | Handrails installation
Note: Handrails installation as per design drawings, specification and engineers’ directions with all required activities
B.10.a | Handrail | Lm | 21
B.11 | Covering parapet wall with 24 gauge GI
Note: Covering the top of the parapet wall with 24 gauge GI sheet as per design drawings, specification and engineers’ directions with all required activities.
B.11.a | Parapet | m2 | 6
B.12 | Water Closet for disabled people
Note: Water closet for disabled people complete set as per design drawings, specification and engineers’ directions with all required activities.
B.12.a | Water Closet | No | 1
B.13 | Water Tank (hand wash facility) complete Set
Note: Water tank (30x60x105) GI sheet 18 gauge ,hand wash basin GI sheet 18 gauge, water tap and with water inlet and sewerge pipes as per design drawings, specification and engineers’ directions with all required activities.
B13.1a | Water tank | No | 1
Total of B- Finishing
Summary
Total of A- Civil Works
Total of B- Finishing
Grand Total

## Construction of Hand Washing
Construction of Hand Washing Facility
S.No | Description of Work and Activities | Unit | Quantity | Unit Rate (AFN) | Total (AFN)
A-Civil Works
A.1 | Site preparation
Note: Site preparation this include site leveling (excavation or backfilling) removing any trees, vegetation, debris, or other obstructions from the construction site as per specification and engineers directions with all required activities.
A.1.a | Construction Area | m2 | 20
A.2 | Excavation
Note: Excavation of all types of lands for foundation, Walkway and floor as per design drawings and specifications with all required activities
A.2.a | Foundation | m3 | 0.9
A.2.b | Side Walk | m3 | 2.75
A.2.c | Floor | m3 | 1.5
A.3 | PCC (M150)
Note: PCC (M150) for foundations with formworks and anchor bolts as per design drawings, specification and engineers’ directions and all required activities
A.3.a | Foundation | m3 | 0.7
A.3.b | Side Walk | m3 | 1
A.3.c | Floor | m3 | 1.994
A.3.d | Floor under water tank | m3 | 0.4
A.4 | Water Tank Stand
Note: Supply and Installation of water tank stand from profile 40x60mm T=2mm with hieght of 0.77 mas per design drawings, specification and engineers’ directions and all required activities
A.4.a | Stand | m2 | 1.5
A.5 | Shelter and shade structure
Note: Supply and installation of shelter and shade structure for hand washing facility (flat calculation) as per design drawings, specification and engineers’ directions and all required activities
A.5.a | Shade structure | m2 | 9
A.6 | Water Tank
Note: Supply and installation of a 20 Gauge (GI) water tank with capacity of 1000 litter, wrapped in parachute fabric and connected to water supply system as per design drawings, specification and engineers’ directions and all required activities.
A.6.a | Water Tank | No | 1
A.7 | 4” diameter (GI) pipe with 2' angle iron
Note:Supply and installation of 4” diameter (GI) pipe with 2' angle iron supports with all accessories and fittings as per design drawings, specification and engineers’ directions and all required activities.
A.7.a | Pipe | Lm | 2.75
A.8 | 3” diameter (GI) Columns
Note:Supply and installation of 3” diameter (GI) pipe for shades supports with all accessories as per design drawings, specification and engineers’ directions and all required activities.
A.8.a | Column | Lm | 18.5
A.9 | tap 1/2" along with 1/2" pipes
Note:Supply and installation of nickel tap 1/2" along with 1/2" pipes with all accessories and fittings as per design drawings, specification and engineers’ directions and all required activities.
A.9.a | tap 1/2" along with 1/2" pipes | Lm | 10
A.10 | PPR 32 mm diameter
Note:Supply and installation of PPR 32 mm diameter for external water usage as per design drawings, specification and engineers’ directions and all required activities.
A.10.a | Pipe | Lump Sum | 1
Total of A- Civil Works

## Construction of Boundary Wall
Construction of Boundary Wall
S.No | Description of Work and Activities | Unit | Quantity | Unit Rate (AFN) | Total (AFN)
A-Civil Works
A.1 | Site preparation
Note: Site preparation this include site leveling (excavation or backfilling) removing any trees, vegetation, debris, or other obstructions from the construction site as per specification and engineers directions with all required activities.
A.1.a | Boundary Wall length | L.m | 310
A.2 | Excavation
Note: Excavation of all types of lands for foundation as per design drawings and specifications with all required activities
A.2.a | Foundation for gate | m3 | 1.75
A.2.b | Foundation Under Walls | m3 | 195.3
A.3 | BAckfilling
Note: filling with soil including levelling and compaction as per design drawings, specification, and engineer directions with all required activities.
A.3.a | Back filling Foundation | m3 | 3
A.3.b | Backfilling under walls | m3 | 43.4
A.4 | Stone masonry
Note: Stone masonry in foundations and above foundation, with M1:4 as per design drawings, specification and engineers’ directions with all required activities
A.4.b | Stone masonry | m3 | 248
A.5 | Burnt brick masonry
Note: Burnt brick masonry with M1:4 as per design drawings, specification and engineers’ directions with all required activities
A.5.a | Walls | m3 | 127.1
A.6 | Plaster Work
Note: plaster walls motor shall be M1:3 as per design drawings, specification and engineers’ directions with all required activities
A.6.a | Wall | m2 | 1085
A.7 | PCC (M150)
Note: PCC (M150) with formworks as per design drawings, specification and engineers’ directions with all required activities
A.7.a | At the top of Stone Masonry | m3 | 27.9
A.7.b | At the top of burnt brick wall | m3 | 12.4
A.8 | RCC (M250)
Note: RCC (M250) with form works as per design drawings, specification and engineers’ directions with all required activities
A.8.a | Column | m3 | 1.2
A.8.b | Footing | m3 | 0.8
A.9 | Main Gate
Note: Supply and installation steel gates for school entrance as per design drawings, specification and engineers’ directions with all required activities
A.9.a | Main Gate (3m × 2.2m) | no | 1
A.9.b | Pedestrain Gate (1.2m × 2.2m) | no | 1
A.10 | Stone pointing
Note: Stone masonry (beaded pointing) with M1:3 as per design drawings, specification and engineers’ directions with all required activities
A.10.a | Stone Pointing | m2 | 310
A.11 | Painting Works
Note: Exterior latex wall and parapet painting 100 % (3 coat) with plaster texture filling as per design drawings, specification and engineers’ directions with all required activities
A.11.a | Wall | m2 | 1085
Total of A- Civil Works

## Summary of Elements
Construction of Shahid Sardar Wali Primary School
No | SUMMARY OF ELEMENTS | TOTAL AFN
1 | Site mobilization and de-mobilization
2 | Construction of 6 + 1 classrooms
3 | Construction of 4 +1 dry latrine
4 | Construction of hand washing facility
5 | Construction of Boundary wall
Grand Total |  | 0