## Annex # 1 sherabad olya
CARE Afghanistan
CBARD project
Balkh Sub office
Annex #1
Company Name( )
Shirabad Olya irrigation canal rehabilitation Bill of Quantity(BoQ)
ID-number | AFG-CARE-CABARD-BLK-DHDI-IRR-001
Province: | Balkh
District: | Dehdadi
Village: | Shirabad Olya |  |  | Date:
Type of Structure:Canal linig
No. | Description of work | Quantity | Unit | Unit Cost AFN | Total Cost AFN | Remarks
Canal lining:
1 | Excavation of foundations | 1533.75 | m3 |  | 0
2 | PCC of Under foundations M-150 (1:2:4) | 101.25 | m3 |  | 0 | see the drawings
3 | Crushed Stone Masonry with Mortar M-300 (1:4) | 972.75 | m3 |  | 0 | see the drawings
4 | Shuttering for Top of Wall and and Expansion Joint | 339 | m2 |  | 0 | see the drawings
5 | PCC for Top of wall M-200 (1:1.5:3) | 73.7 | m3 |  | 0 | see the drawings
6 | PCC for bed of canal & expansion joints M200 (1:1.5:3) | 67.3 | m3 |  | 0 | Expansion joints have water stopper and kack with Aqumat admixture
7 | Pointing of Enternal sides of walls with Mortor & water proof admixture M-400(1:3) | 1125 | m2 |  | 0 | see the drawings
8 | Pointing of External sides of walls with Martor M-400(1:3) | 1125 | m2 |  | 0
9 | Filling of bed of Canal with Gravel (under PCC) | 28.13 | m3 |  | 0 | compaction must be done with small compactor machine
10 | Back filling of excavation and site clearance | 496.88 | m3 |  | 0 | compaction must be done with small compactor machine
11 | Project Sign Board,acoording to standard size as per attached drawing | 1 | pcs |  | 0 | see the drawings
Total Cost AFN for Annex # 1 |  |  |  |  | 0