## Sheet1
Province: | Kunduz | Months
District: | Archi, Chardara, Imam sahib and Khan abad | I |  |  |  | II
Villages: |  | Weeks
Project Purpose: Rehabilitation/Renovation and medical waste management |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
HF#01 | Imam Sahib Health Facility:
1.01 | Rehabilitation of the building (include doors and windows repairing, painting etc…)
1.02 | Construction of two waiting area, (10 x 4) m (one for male and one for female).
1.03 | Toilets Construction Only for female
1.04 | Construction of Wast Management facilities, (incinerator, Ash pit, Sharp Pit, placenta Pits, Soak pit.
1.05 | Construction of boundary fence for WM area ( 14 length x 1.2 high ) m.
1.06 | Construction of new water wells (30) m
1.07 | Provision of Solar panels and improvement of building electricity.
1.08 | Construction of new septic tank (3.4 x 2.4) m.
1.09 | Construction of footpath (61.5) m2
1.1 | Construction of new guard room (3 x 3) m.
1.11 | Improvement of HF Water supply network.
1.12 | Improvement of HF sewage system.
1.13 | Project Close out and Handover
HF#02 | Chardarah Health Facilities:
2.01 | Rehabilitation of the building (include doors and windows repairing, painting etc…)
2.02 | improvement of building electricity.
2.03 | Construction of new guard room (3 x 3) m.
2.04 | Construction of new septic tank (3.4 x 2.4) m.
2.05 | Construction of new water wells (30) m
2.06 | Construction of two waiting area, (10 x 4) m (one for male and one for female)
2.07 | Toilets Construction two in number (Male and Female) .
2.08 | Construction of Wast Management facilities, (incinerator, Ash pit, Sharp Pit, placenta Pits, Soak pit).
2.09 | Construction of boundary fence ( 18 m length x 1.2 high )
2.1 | Construction of footpath (103.5) m2
2.11 | Improvement of HF Water supply network.
2.12 | Improvement of HF sewage system.
2.13 | Project Close out and Handover
HF#03 | Khan Abad Health Facilities:
3.01 | Rehabilitation of the building (include doors and windows repairing, painting etc…)
3.02 | Provision of Solar panels and improvement of building electricity.
3.03 | Construction of two waiting area, (10 x 4) m (one for male and one for female).
3.04 | Construction of new septic tank (3.4 x 2.4) m.
3.05 | Construction Brick masonry Boundary wall (120) m.
3.06 | Construction of Wast Management facilities, (incinerator, Ash pit, Sharp Pit, placenta Pits, Soak pit).
3.07 | Construction of boundary fence ( 14 m length x 1.2 m hight).
3.08 | Construction of digging new water wells ( 30 m depth).
3.09 | Toilets Construction two in number (Male and Female) .
3.1 | Construction of new guard room (3 x 3) m.
3.11 | Construction of footpath (90) m2
3.12 | Improvement of HF Water supply network.
3.13 | Improvement of HF sewage system.
3.14 | Project Close out and Handover
HF#04 | Archi Health Facility:
4.01 | Rehabilitation of the building (include doors and windows repairing, painting etc…)
4.02 | Construction of two waiting area, (10 x 4) m (one for male and one for female).
4.03 | Provision of Solar panels and improvement of building electricity.
4.04 | Digging of new water well
4.05 | Rehabilitation and improvement of existing toilets (4 in numbers).
4.06 | Construction of Wast Management facilities, (incinerator, Ash pit, Sharp Pit, placenta Pits, Soak pit).
4.07 | Construction of boundary fence ( 18 m length x 1.2 m hight)
4.08 | Improvement of HF Water supply network.
4.09 | Improvement of HF sewage system.
4.1 | Construction of culvert (one in number).