## Measurements (hidden)
No | Activity | Description | Unit | No | Length | Width | Depth | Total | Remarks
1 | Site prepration
| Site prepration | Construction Area | Lump Sum | 1 |  |  |  | 1
Total | [7 empty] | 1
1 | Exterior plaster Repairing
| Exterior Plaster | Axis A | m2 | 1 | 25.89 |  | 2.6 | 67.314
|  | Axis C | m2 | 2 | 10.3 |  | 2.6 | 53.56
|  | Axis D | m2 | 2 | 1.18 |  | 2.6 | 6.136
|  | Axis F | m2 | 1 | 7.89 |  | 2.6 | 20.514
|  | Axis 1,7 | m2 | 2 | 7.5 |  | 2.6 | 39
|  | Axis 3,5 | m2 | 2 | 8.24 |  | 2.6 | 42.848
|  | Axis 3,5 | m2 | 2 | 3.78 |  | 2.6 | 19.656
|  | Parapet | m2 | 1 | 26 |  | 0.5 | 13
Total | [7 empty] | 262.028
2 | Exterior Painting
| Exterior Plaster | Axis A | m2 | 1 | 25.89 |  | 2.6 | 67.314
|  | Axis C | m2 | 2 | 10.3 |  | 2.6 | 53.56 |  | 2.05
|  | Axis D | m2 | 2 | 1.18 |  | 2.6 | 6.136
|  | Axis F | m2 | 1 | 7.89 |  | 2.6 | 20.514
|  | Axis 1,7 | m2 | 2 | 7.5 |  | 2.6 | 39
|  | Axis 3,5 | m2 | 2 | 8.24 |  | 2.6 | 42.848
|  | Axis 3,5 | m2 | 2 | 3.78 |  | 2.6 | 19.656
|  | Parapet | m2 | 1 | 101 |  | 2.55 | 257.55
Total | [7 empty] | 506.578
2 | Interior Plaster Repairing
| Interior Plaster for walls | Entity N | m2 | 1 | 8.77 | 1.25 |  | 10.9625
|  | Entity M | m2 | 1 | 4.41 | 0.5 |  | 2.205
|  | Entity L | m2 | 1 | 3 | 0.5 |  | 1.5
|  | Entity K | m2 | 1 | 6.42 | 2 |  | 12.84
|  | Entity H | m2 | 1 | 6.65 | 2.5 |  | 16.625
|  | Entity I | m2 | 1 | 3 | 0.5 |  | 1.5
|  | Entity F | m2 | 1 | 0.5 | 0.5 |  | 0.25
|  | Entity F' | m2 | 1 | 1 | 2.5 |  | 2.5
|  | Entity A | m2 | 1 | 2 | 0.5 |  | 1
|  | Entity B | m2 | 1 | 9.5 | 2.5 |  | 23.75
|  | Entity D | m2 | 1 | 5.16 | 1.2 |  | 6.192
Total | [7 empty] | 79.3245
| Interior Plaster for ceilling | Entity M | m2 | 1 | 2 | 1 |  | 2
|  | Entity L | m2 | 1 | 4.4 | 3 |  | 13.2
|  | Entity K | m2 | 1 | 3 | 3 |  | 9
|  | Entity H | m2 | 1 | 3 | 2 |  | 6
|  | Entity I | m2 | 1 | 1 | 1 |  | 1
|  | Entity J | m2 | 1 | 3 | 2 |  | 6
|  | Entity G | m2 | 1 | 2 | 2.5 |  | 5
|  | Entity F | m2 | 1 | 1.5 | 3.5 |  | 5.25
|  | Entity F' | m2 | 1 | 2 | 5 |  | 10
|  | Entity A | m2 | 1 | 4 | 2 |  | 8
|  | Entity B | m2 | 1 | 2 | 2.5 |  | 5
|  | Entity D | m2 | 1 | 1 | 1 |  | 1
|  | Entity C | m2 | 1 | 3 | 1.5 |  | 4.5
Total | [7 empty] | 75.95
3 | Interior Painting
| Interior paint for walls | Entity A | m2 | 1 | 12.59 | 2.5 |  | 31.475
|  | Entity B | m2 | 1 | 22.26 | 2.5 |  | 55.65
|  | Entity F' | m2 | 1 | 20.95 | 2.5 |  | 52.375
|  | Entity F | m2 | 1 | 13.64 | 2.5 |  | 34.1
|  | Entity H | m2 | 1 | 15 | 2.5 |  | 37.5
|  | Entity I | m2 | 1 | 24.22 | 2.5 |  | 60.55
|  | Entity K | m2 | 1 | 13.42 | 2.5 |  | 33.55
|  | Entity L | m2 | 1 | 15 | 2.5 |  | 37.5
|  | Entity M | m2 | 1 | 17.2 | 2.5 |  | 43
|  | Entity N | m2 | 1 | 16 | 2.5 |  | 40
Total | [7 empty] | 425.7
| Interior paint for ceilling | Entity A | m2 | 1 | 3.77 | 4.91 |  | 18.5107
|  | Entity B | m2 | 1 | 4.05 | 7.08 |  | 28.674
|  | Entity C | m2 | 1 | 3 | 1.5 |  | 4.5
|  | Entity D | m2 | 1 | 5.16 | 3 |  | 15.48
|  | Entity F' | m2 | 1 | 9.53 | 1.9 |  | 18.107
|  | Entity f | m2 | 1 | 3.45 | 3.37 |  | 11.6265
|  | Entity G | m2 | 1 | 2.39 | 2 |  | 4.78
|  | Entity H | m2 | 1 | 4.38 | 4 |  | 17.52
|  | Entity I | m2 | 1 | 5.45 | 6.66 |  | 36.297
|  | Entity J | m2 | 1 | 3 | 2 |  | 6
|  | Entity K | m2 | 1 | 3.21 | 3.45 |  | 11.0745
|  | Entity L | m2 | 1 | 4.5 | 3 |  | 13.5
|  | Entity M | m2 | 1 | 4.5 | 4.11 |  | 18.495
|  | Entity L | m2 | 1 | 4.5 | 3.4 |  | 15.3
|  | Entity M | m2 | 1 | 2 | 1.7 |  | 3.4
Total | [7 empty] | 223.2647
3 | Windows Adjustment
|  | Windows | No | 25 |  |  |  | 25
Total | [7 empty] | 25
4 | Installation of Doors
| Doors | D1 | m2 | 8 | 1 | 2.5 |  | 20
|  | D2 | m2 | 4 | 0.8 | 2.5 |  | 8
|  | Dw1 | m2 | 1 | 1.97 | 2.5 |  | 4.925
|  | Dw2 | m2 | 2 | 3.77 | 2.5 |  | 18.85
Total | [7 empty] | 51.775
5 | Floor tiles
| Floor | Entity A | m2 | 1 | 3.77 | 4.91 |  | 18.5107
|  | Entity B | m2 | 1 | 4.05 | 7.08 |  | 28.674
|  | Entity D | m2 | 1 | 2.95 | 5.16 |  | 15.222
|  | Entity F' | m2 | 1 | 1.9 | 9.53 |  | 18.107
|  | Entity F | m2 | 1 | 3.37 | 3.45 |  | 11.6265
|  | Entity H | m2 | 1 | 4.38 | 3.96 |  | 17.3448
|  | Entity I | m2 | 1 | 6.66 | 5.45 |  | 36.297
|  | Entity K | m2 | 1 | 3.21 | 3.45 |  | 11.0745
|  | Entity L | m2 | 1 | 4.4 | 3 |  | 13.2
|  | Entity M | m2 | 1 | 4.4 | 4.11 |  | 18.084
|  | Entity N | m2 | 1 | 4.4 | 3.4 |  | 14.96
Total | [7 empty] | 203.1005
6 | Roof Repairing
| Roof | Roof | m2 | 1 | 135.069 |  |  | 135.069
Total | [7 empty] | 135.069
7 | Toilets Tiles
| Toilet Floor | Toilet C | m2 | 1 | 3 | 1.5 |  | 4.5
|  | Toilet O | m2 | 1 | 1.65 | 1.9 |  | 3.135
|  | Tolet G | m2 | 1 | 2.4 | 2 |  | 4.8
|  | Toilet J | m2 | 1 | 3.3 | 2.1 |  | 6.93
Total | [7 empty] | 19.365
8 | Toilets wall Tiles
| Toilet Walls | Toilet C | m2 | 1 | 9 | 2.5 |  | 22.5
|  | Toilet O | m2 | 1 | 7.04 | 2.5 |  | 17.6
|  | Tolet G | m2 | 1 | 8.78 | 2.5 |  | 21.95
|  | Toilet J | m2 | 1 | 10.78 | 2.5 |  | 26.95
|  | kitchen | m2 | 1 | 16.32 | 2.5 |  | 40.8
Total | [7 empty] | 89
9 | Kitchen Cup Boards
| Kitchen | Cup Boards | m2 | 1 | 3.25 |  | 0.6 | 1.95
Total | [7 empty] | 1.95
10 | Kitchen Desk
| Kitchen | Desk | m2 | 1 | 5.75 |  | 0.9 | 5.175
Total | [7 empty] | 5.175
12 | Pointing Paint
| wall | paint | m2 | 1 | 101 |  | 0.5 | 50.5
Total | [7 empty] | 50.5
12 | PVC Doors
| D1 |  | m2 | 1 | 3.8 |  | 2.5 | 9.5
| D2 |  |  | 2 | 2 |  | 2.5 | 10
Total | [7 empty] | 19.5
12 | Skirt Wall
| wall |  | Lm | 1 | 160 |  |  | 160
Total | [7 empty] | 160

## Summary
Renovation of (Malik Tajikia Girls Primary School )
The cost for all items in this BOQ, in general, includes deploying any machinery, and manpower, and carrying out any relocations/ removal/ salvage/ disposal /reinstating tasks. The costs of checking and testing for all items and materials that need to be used should be included in the relevant unit cost of related items. However, particular issues with the costs of items are mentioned under each section in this BOQ. Details of work method & and equipment/machinery for different types of work shall be brought to the attention of the Engineer to get approval of the Engineer before commencing the jobs. Read all project documents before pricing the job. Changes in market prices during the project period for any item are the responsibility of the Contractor without any extra payment. For all the finishing, electrical accessories, structural items & and materials, mechanical accessories/equipment, plumbing-related materials/items, and other equipment that are mentioned in this BoQ and going to be used, samples, product data from manufacturers/companies, certificates should be submitted to Client in charge Engineer and get their approvals from in charge engineer before start the activity or use the materials and accessories in the project. The contractor has to produce the manufacturer approval certificate of the production country for all the major construction materials and the ISO certificate. The contractor must provide samples, mockups, and catalogs for testing/inspection and approval by the site engineer, The Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. The contractor must provide PPE for all laborers, personnel, engineers, and possible visitors to the site.
S.N | Items (Bill) | Cost (AFN)
1 | Total B1. Construction of Latrine: | 0
2 | Total of C1. Renovation of School Buildin: | 0
| Grand total amount in AFN | 0
`

## B. Latrine 5 Cells
Construction of ( Latrine for Malik Tajikia Girls Primary School )
The following text outlines important guidelines that must be followed during the project. It is important to clarify that the total cost of all items listed in this BOQ includes the deployment of machinery and manpower, as well as any relocation, removal, salvage, or reinstatement tasks. It is also important to note that the cost of checks and testing for items and materials to be used must be included in the relevant unit cost of related items. However, specific issues with the costs of items are mentioned under each section in this BOQ. Before commencing any job, details of work methods and equipment/machinery for different types of work must be brought to the attention of the Engineer for approval. Furthermore, it is important to read all project documents before pricing the job. Any changes in market prices during the project period for any item are the contractor's responsibility without any extra payment. To ensure quality and safety, all finishing, electrical accessories, structural items and materials, mechanical accessories/equipment, plumbing-related materials/items, and other equipment mentioned in this BOQ and going to be used must be approved by the Client in charge Engineer before starting the activity or using the materials and accessories in the project. The approval process involves submitting samples, product data from manufacturers/companies, and certificates. The contractor must also provide the manufacturer approval certificate of the production country for all major construction materials and the ISO certificate. Samples, mockups, and catalogs for testing/inspection and approval by the site engineer must be provided by the contractor. The Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. Finally, the contractor must provide Personal Protective Equipment (PPE) for all laborers, personnel, engineers, and visitors to the site to ensure their safety during the project
Sar-e-Pol Province, Sozma Qala district Malik Tajikia Girls Primary School
Priority 2 Construction of latrine with 5 cells
B - Construction of latrine |  | Unit | Quantity | Unit price (AFN) | Total cast (AFN) | Remark
S.N | Description
B. Civil Works:
B1 | Excavation of foundation & walkways in Grad 3 land Prepare all materials, equipment, and manpower for excavation of foundation in type 3 land with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 30 |  | 0
B2 | Stone Masonry of foundation with 1:5 mortar Prepare all materials, equipment, and manpower for stone masonry work in foundation with cement ratio 1:5 with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 27 |  | 0
B3 | Supper Stone Masonry with cement mortar 1:4 Prepare all materials, equipment, and manpower for stone masonry work top of the foundation with cement ratio 1:4 with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 43 |  | 0
B4 | RCC(1:1.5:3) rings on the top of supper stone masonry 20cm Prepare all materials, equipment, and manpower for casting 20 MPA RCC for rings including steel bending work, curing, formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 4.5 |  | 0
B5 | Filling of flooring with soil including compaction 35cm Prepare all materials, equipment, and manpower for back filling of flooring with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 13.3 |  | 0
B6 | Filling of floor & walkways with gravel including compaction 15cm. Prepare all materials, equipment, and manpower for back filling of flooring and walkways with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 5 |  | 0
B7 | Bricks masonry burnt bricks with (1:5) mortar 35 cm Prepare all materials, equipment, and manpower for burnt brick wall with mortar 1:5 for 35, 25, 15cm wall with formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 27 |  | 0
B8 | RCC(1:1.5:3) rings on the top of brick masonry 20cm Prepare all materials, equipment, and manpower for casting 20 MPA RCC for rings including steel bending work, curing, formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 2.25 |  | 0
B9 | PCC(1:2:4) of flooring, stair & walkways ( Mark 150) with 10 cm thickness Prepare all materials, equipment, and manpower for casting 15 MPA PCC for floors, sidewalk and ramp with formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 7 |  | 0
B10 | Steel I beam and lintel #14 Prepare all materials, equipment, and manpower for steel I BM #14cm with welds and all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M/L | 48 |  | 0
B11 | Oil painting of steel I beam 2 coat. Prepare all materials, equipment, and manpower for I BMs oil painting with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M/L | 48 |  | 0
B12 | Planking work over wooden beam ( thickness 3 cm). Prepare all materials, equipment, and manpower for wooden plank 3cm on I BM with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 24 |  | 0
B13 | Mat( Borya) work over planking. Prepare all materials, equipment, and manpower for Mat (Borya) on planking with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 24 |  | 0
B14 | Clay and dry soil over Mat( Borya) 15 cm Thick. Prepare all materials, equipment, and manpower for Mat (Borya) on planking with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 24 |  | 0
B15 | Wooden truss with Iron sheeting front Khar wood and 24 gauge inron sheet Prepare all materials, equipment, and manpower for wooden truss and iron sheet 24G with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 33.5 |  | 0
B16 | Mud plaster ( kagel) 2 coats including plastic one layer Prepare all materials, equipment, and manpower for straw mud plaster with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 27 |  | 0
B17 | Making and installation of prefabricate slab according to the drawing Prepare all materials, equipment, and manpower for providing and installing of prefabricate slab with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Ea. | 12 |  | 0
B18 | Gutters work (Vertical from GI sheet 24 gage 10X15 cm) Prepare all materials, equipment, and manpower for gutters GI sheet 24 G 10x15cm with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M/L | 8 |  | 0
B19 | Inside Plaster work (1:4) Mortar with smooth finishing (Namd Mali) Prepare all materials, equipment, and manpower for plastering 1:4 with 2cm thickness including curing, best surfacing preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 118 |  | 0
B20 | White washing insid side with 65% emulsion Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 60% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 118 |  | 0
B21 | Carpentry work (Making of Window Complete) Prepare all materials, equipment, and manpower for carpentry work with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 4.4 |  | 0
B22 | Carpentry work (Making of single doors Complete) Prepare all materials, equipment, and manpower for carpentry work with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 9.4 |  | 0
B23 | Oil painting of windows and doors( 3 coats) Prepare all materials, equipment, and manpower for window and door oil painting with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 27.5 |  | 0
B24 | Installation of glasses 4mm with chufti Prepare all materials, equipment, and manpower for installation of glasses 4mm with chufti and other related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 4.4 |  | 0
B25 | Out side plaster work (with 1: 4 motor) and smooth finishing (Namad mali) Prepare all materials, equipment, and manpower for plastering 1:4 with 2cm thickness including curing, best surfacing preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 83.5 |  | 0
B26 | White washing with 100 % plastic emulsion (outside) Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 100% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 78 |  | 0
B27 | Installation of fly screen with chufti complete Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 100% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 2 |  | 0
B28 | Pointing with 1:3 mortar Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 100% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 55 |  | 0
B29 | Making of handrail Prepare all materials, equipment, and manpower for the preparation of 10.5m length 80cm high and Painting of Steel handrails with oil paint on three coats with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | M/L | 10.5 |  | 0
B30 | PVC 4 inch pipe for ventilation Prepare all materials, equipment, and manpower for installation of 4inch PVC pipe for ventilation with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | M/L | 25 |  | 0
B31 | Preparation and Installation GI water tank 30x60x105cm and sank in the corridor. Prepare all materials, equipment, and manpower for installation of water tank and sank in corridor with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | Ea. | 1 |  | 0
B32 | Preparation and Installation grabs Prepare all materials, equipment, and manpower for supplying and installation of grabs with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | Ea. | 2 |  | 0
| Total of C1. Civil Works: |  |  |  | 0

## C. School renovation
Renovation of ( Malik Tajikia Girls Primary School )
The following text outlines important guidelines that must be followed during the project. It is important to clarify that the total cost of all items listed in this BOQ includes the deployment of machinery and manpower, as well as any relocation, removal, salvage, or reinstatement tasks. It is also important to note that the cost of checks and testing for items and materials to be used must be included in the relevant unit cost of related items. However, specific issues with the costs of items are mentioned under each section in this BOQ. Before commencing any job, details of work methods and equipment/machinery for different types of work must be brought to the attention of the Engineer for approval. Furthermore, it is important to read all project documents before pricing the job. Any changes in market prices during the project period for any item are the contractor's responsibility without any extra payment. To ensure quality and safety, all finishing, electrical accessories, structural items and materials, mechanical accessories/equipment, plumbing-related materials/items, and other equipment mentioned in this BOQ and going to be used must be approved by the Client in charge Engineer before starting the activity or using the materials and accessories in the project. The approval process involves submitting samples, product data from manufacturers/companies, and certificates. The contractor must also provide the manufacturer approval certificate of the production country for all major construction materials and the ISO certificate. Samples, mockups, and catalogs for testing/inspection and approval by the site engineer must be provided by the contractor. The Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. Finally, the contractor must provide Personal Protective Equipment (PPE) for all laborers, personnel, engineers, and visitors to the site to ensure their safety during the project
Sar-e-Pol Province, Sozma Qala district Malik Tajikia Girls Primary School
Priority 3 School Building Renovation
C - School Building Renovation |  | Unit | Quantity | Unit price (AFN) | Total cast (AFN) | Remark
S.N | Description
C. Civil Works:
C1 | Removing the existence damaged Isogam and PCC including wooden plan from the roof Prepare all materials, equipment, and manpower for Removing the existence roof includin Isogam, PCC, piece of bricks and plank board with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M2 | 129 |  | 0
C2 | Roofing work including (Plank board 3cm, water proof tent, peice of brick 5cm, 6cm PCC 1:2:4 with wire mesh 2.7mm and one layer izogam Prepare all materials, equipment, and manpower for roofing work including laying water proof tent, gravels PCC and isogam and 100% plank board 2.5cm with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M2 | 129 |  | 0
C3 | Brick masonry work mortar ratio 1:5 for roof chimney and picks Prepare all materials, equipment, and manpower for brick masonry work with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M3 | 9.7 |  | 0
C4 | Supply and installation of gutters length 3.5m with size of 15cmx10cm Iron sheet 0.5mm Prepare all materials, equipment, and manpower for gutter size of 15x10cm Iron sheet 0.5mm with length of 3.5m and with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | pic | 3 |  | 0
C5 | Exterior and interior wall cement and sand plaster 1:4 Prepare all materials, equipment, and manpower for exterior wall cement and sand Plaster 1:4 with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | M2 | 131 |  | 0
C6 | Stone pitching under ramp and sidewalks with 10cm thinkness Prepare all materials, equipment, and manpower for stone pitching 10cm under sidewalkh and 20cm under ramp with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M3 | 6 |  | 0
C7 | PCC 15MPA for Class floors, veranda, ramps and sidewalk with 6cm thickness Prepare all materials, equipment, and manpower for casting 15 MPA PCC for floors, sidewalk and ramp with formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M3 | 11.6 |  | 0
C8 | Supply and installation of new door and replacement of Door Wooden Pala "Piece" Prepare all materials, equipment, and manpower for the a new door completed with hardware's size 1(2.5x1m) and replacement of door piece "pala" with size 3(1.9x0.9m)within glass hinge, lock handle complete all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval of in charge engineer | M2 | 7.65 |  | 0
C9 | Supply and replacement of Windows Wooden Pala "Piece" Prepare all materials, equipment, and manpower for the replacement of wooden pala with hardware's size 3(1.32x0.43m) and 3(0.65x0.56m)within glass hinge, lock handle complete all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval of in charge engineer | M2 | 2.8 |  | 0
C10 | Adjusting and fixing windows total 15, wooden doors total 4 Prepare all materials, equipment, and manpower for Adjusting wooden windows total of 15 with size of 10(1.8*1)m and 5(1.2*0.7), and wooden doors total 4 with size of 4(2.5*1)m with replacing the accessories as needed (hinges, 4 locks, 25 m2 glasses, chefti 110m, fly screen 11.5m2 with the best quality. with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of in charge engineer | Job | 19 |  | 0
C11 | Interior and exterior plastic paint 100% three coats Prepare all materials, equipment, and manpower for the interior Wall 100% Plastic Paint three coats (Jotun or equivalent) including preparation, sand paper sheet, primer, and filling with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | M2 | 504 |  | 0
C12 | Oil Painting of doors and windows three coats+black board Prepare all materials, equipment, and manpower for window and door oil painting with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M2 | 36 |  | 0
C13 | Supply and installation of handrail for ramp with three coats oil paint. Prepare all materials, equipment, and manpower for the preparation of 7m length 80cm high with 3inch dia best quality and Painting of Steel handrails with oil paint on three coats with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | L/M | 7 |  | 0
C14 | Supply and installation of chimney caps with GI sheet 0.5mm Prepare all materials, equipment, and manpower for chimney caps with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Pic | 4 |  | 0
C15 | Cutting filling leveling and Cleaning of the school area from extra soil with average high of 35cm Prepare all materials, equipment, and manpower for cutting hill material around of sidewalk within 5m and convery it away of the project and clean extra soil, construction materials with all related activities to complete the job as per the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | m2 | 200 |  | 0
C16 | Donor Metal Sign Board 120x80cm as per design and drawings | Pic | 1 |  | 0
Total of C1. Civil Works: |  |  |  |  | 0