## Project Plan for Latrine Const
Organization for Afghan Women Capacity & Knowledge (OAWCK)
WASH project Initiative in Laghman, Jawzjan, and Balkh Provinces
Project Code: CBPF-AFG-24-R-NGO-28003
Project Plan for Construction of Household Latrines
S/No | Description of Activities | Responsible | 2024-07-24 | 2024-08-24 | 2024-09-24 | 2024-10-24 | 2024-11-24 | 2024-12-24 | 2025-01-24 | 2025-02-24 | Remarks
Laghman Province ( Qarghayee, and Alingar districts) |  |  | Timeframe
1 | Construction Work of 40 Household latrines in Alingar district of Laghman Province. | WASH Officers
2 | Construction Work of 40 Household latrines in Qarghayee district of Laghman Province. | WASH Officers
3 | Completion reports, Demobilization, Project hand Over | WASH Officers