## Project Plan for Latrine Const
Organization for Afghan Women Capacity & Knowledge (OAWCK)
WASH project Initiative in Laghman, Jawzjan, and Balkh Provinces
Project Code: CBPF-AFG-24-R-NGO-28003
Plan for the Repairing of Solar Pipe Schemes
S/No | Description of Activities | Responsible | 2024-07-24 | 2024-08-24 | 2024-09-24 | 2024-10-24 | 2024-11-24 | 2024-12-24 | 2025-01-24 | 2025-02-24 | Remarks
Laghman Province ( Qarghayee, and Alingar districts) |  |  | Timeframe
1 | Repairing Work of the BabaAli Pipe Scheme in Sheberghan district of Jawzjan Province. | WASH Officers
| Repairing Work of the Kalata Shakh Pipe Scheme in Khanaqa district of Jawzjan Province. | WASH Officers
3 | Project Completion, Handover and Closing. | WASH Officers