## Measurements (hidden)
No | Activity | Description | Unit | No | Length | Width | Depth | Total | Remarks
1 | Site prepration
| Site prepration | Construction Area | Lump Sum | 1 |  |  |  | 1
Total | [7 empty] | 1
1 | Exterior plaster Repairing
| Exterior Plaster | Axis A | m2 | 1 | 25.89 |  | 2.6 | 67.314
|  | Axis C | m2 | 2 | 10.3 |  | 2.6 | 53.56
|  | Axis D | m2 | 2 | 1.18 |  | 2.6 | 6.136
|  | Axis F | m2 | 1 | 7.89 |  | 2.6 | 20.514
|  | Axis 1,7 | m2 | 2 | 7.5 |  | 2.6 | 39
|  | Axis 3,5 | m2 | 2 | 8.24 |  | 2.6 | 42.848
|  | Axis 3,5 | m2 | 2 | 3.78 |  | 2.6 | 19.656
|  | Parapet | m2 | 1 | 26 |  | 0.5 | 13
Total | [7 empty] | 262.028
2 | Exterior Painting
| Exterior Plaster | Axis A | m2 | 1 | 25.89 |  | 2.6 | 67.314
|  | Axis C | m2 | 2 | 10.3 |  | 2.6 | 53.56 |  | 2.05
|  | Axis D | m2 | 2 | 1.18 |  | 2.6 | 6.136
|  | Axis F | m2 | 1 | 7.89 |  | 2.6 | 20.514
|  | Axis 1,7 | m2 | 2 | 7.5 |  | 2.6 | 39
|  | Axis 3,5 | m2 | 2 | 8.24 |  | 2.6 | 42.848
|  | Axis 3,5 | m2 | 2 | 3.78 |  | 2.6 | 19.656
|  | Parapet | m2 | 1 | 101 |  | 2.55 | 257.55
Total | [7 empty] | 506.578
2 | Interior Plaster Repairing
| Interior Plaster for walls | Entity N | m2 | 1 | 8.77 | 1.25 |  | 10.9625
|  | Entity M | m2 | 1 | 4.41 | 0.5 |  | 2.205
|  | Entity L | m2 | 1 | 3 | 0.5 |  | 1.5
|  | Entity K | m2 | 1 | 6.42 | 2 |  | 12.84
|  | Entity H | m2 | 1 | 6.65 | 2.5 |  | 16.625
|  | Entity I | m2 | 1 | 3 | 0.5 |  | 1.5
|  | Entity F | m2 | 1 | 0.5 | 0.5 |  | 0.25
|  | Entity F' | m2 | 1 | 1 | 2.5 |  | 2.5
|  | Entity A | m2 | 1 | 2 | 0.5 |  | 1
|  | Entity B | m2 | 1 | 9.5 | 2.5 |  | 23.75
|  | Entity D | m2 | 1 | 5.16 | 1.2 |  | 6.192
Total | [7 empty] | 79.3245
| Interior Plaster for ceilling | Entity M | m2 | 1 | 2 | 1 |  | 2
|  | Entity L | m2 | 1 | 4.4 | 3 |  | 13.2
|  | Entity K | m2 | 1 | 3 | 3 |  | 9
|  | Entity H | m2 | 1 | 3 | 2 |  | 6
|  | Entity I | m2 | 1 | 1 | 1 |  | 1
|  | Entity J | m2 | 1 | 3 | 2 |  | 6
|  | Entity G | m2 | 1 | 2 | 2.5 |  | 5
|  | Entity F | m2 | 1 | 1.5 | 3.5 |  | 5.25
|  | Entity F' | m2 | 1 | 2 | 5 |  | 10
|  | Entity A | m2 | 1 | 4 | 2 |  | 8
|  | Entity B | m2 | 1 | 2 | 2.5 |  | 5
|  | Entity D | m2 | 1 | 1 | 1 |  | 1
|  | Entity C | m2 | 1 | 3 | 1.5 |  | 4.5
Total | [7 empty] | 75.95
3 | Interior Painting
| Interior paint for walls | Entity A | m2 | 1 | 12.59 | 2.5 |  | 31.475
|  | Entity B | m2 | 1 | 22.26 | 2.5 |  | 55.65
|  | Entity F' | m2 | 1 | 20.95 | 2.5 |  | 52.375
|  | Entity F | m2 | 1 | 13.64 | 2.5 |  | 34.1
|  | Entity H | m2 | 1 | 15 | 2.5 |  | 37.5
|  | Entity I | m2 | 1 | 24.22 | 2.5 |  | 60.55
|  | Entity K | m2 | 1 | 13.42 | 2.5 |  | 33.55
|  | Entity L | m2 | 1 | 15 | 2.5 |  | 37.5
|  | Entity M | m2 | 1 | 17.2 | 2.5 |  | 43
|  | Entity N | m2 | 1 | 16 | 2.5 |  | 40
Total | [7 empty] | 425.7
| Interior paint for ceilling | Entity A | m2 | 1 | 3.77 | 4.91 |  | 18.5107
|  | Entity B | m2 | 1 | 4.05 | 7.08 |  | 28.674
|  | Entity C | m2 | 1 | 3 | 1.5 |  | 4.5
|  | Entity D | m2 | 1 | 5.16 | 3 |  | 15.48
|  | Entity F' | m2 | 1 | 9.53 | 1.9 |  | 18.107
|  | Entity f | m2 | 1 | 3.45 | 3.37 |  | 11.6265
|  | Entity G | m2 | 1 | 2.39 | 2 |  | 4.78
|  | Entity H | m2 | 1 | 4.38 | 4 |  | 17.52
|  | Entity I | m2 | 1 | 5.45 | 6.66 |  | 36.297
|  | Entity J | m2 | 1 | 3 | 2 |  | 6
|  | Entity K | m2 | 1 | 3.21 | 3.45 |  | 11.0745
|  | Entity L | m2 | 1 | 4.5 | 3 |  | 13.5
|  | Entity M | m2 | 1 | 4.5 | 4.11 |  | 18.495
|  | Entity L | m2 | 1 | 4.5 | 3.4 |  | 15.3
|  | Entity M | m2 | 1 | 2 | 1.7 |  | 3.4
Total | [7 empty] | 223.2647
3 | Windows Adjustment
|  | Windows | No | 25 |  |  |  | 25
Total | [7 empty] | 25
4 | Installation of Doors
| Doors | D1 | m2 | 8 | 1 | 2.5 |  | 20
|  | D2 | m2 | 4 | 0.8 | 2.5 |  | 8
|  | Dw1 | m2 | 1 | 1.97 | 2.5 |  | 4.925
|  | Dw2 | m2 | 2 | 3.77 | 2.5 |  | 18.85
Total | [7 empty] | 51.775
5 | Floor tiles
| Floor | Entity A | m2 | 1 | 3.77 | 4.91 |  | 18.5107
|  | Entity B | m2 | 1 | 4.05 | 7.08 |  | 28.674
|  | Entity D | m2 | 1 | 2.95 | 5.16 |  | 15.222
|  | Entity F' | m2 | 1 | 1.9 | 9.53 |  | 18.107
|  | Entity F | m2 | 1 | 3.37 | 3.45 |  | 11.6265
|  | Entity H | m2 | 1 | 4.38 | 3.96 |  | 17.3448
|  | Entity I | m2 | 1 | 6.66 | 5.45 |  | 36.297
|  | Entity K | m2 | 1 | 3.21 | 3.45 |  | 11.0745
|  | Entity L | m2 | 1 | 4.4 | 3 |  | 13.2
|  | Entity M | m2 | 1 | 4.4 | 4.11 |  | 18.084
|  | Entity N | m2 | 1 | 4.4 | 3.4 |  | 14.96
Total | [7 empty] | 203.1005
6 | Roof Repairing
| Roof | Roof | m2 | 1 | 135.069 |  |  | 135.069
Total | [7 empty] | 135.069
7 | Toilets Tiles
| Toilet Floor | Toilet C | m2 | 1 | 3 | 1.5 |  | 4.5
|  | Toilet O | m2 | 1 | 1.65 | 1.9 |  | 3.135
|  | Tolet G | m2 | 1 | 2.4 | 2 |  | 4.8
|  | Toilet J | m2 | 1 | 3.3 | 2.1 |  | 6.93
Total | [7 empty] | 19.365
8 | Toilets wall Tiles
| Toilet Walls | Toilet C | m2 | 1 | 9 | 2.5 |  | 22.5
|  | Toilet O | m2 | 1 | 7.04 | 2.5 |  | 17.6
|  | Tolet G | m2 | 1 | 8.78 | 2.5 |  | 21.95
|  | Toilet J | m2 | 1 | 10.78 | 2.5 |  | 26.95
|  | kitchen | m2 | 1 | 16.32 | 2.5 |  | 40.8
Total | [7 empty] | 89
9 | Kitchen Cup Boards
| Kitchen | Cup Boards | m2 | 1 | 3.25 |  | 0.6 | 1.95
Total | [7 empty] | 1.95
10 | Kitchen Desk
| Kitchen | Desk | m2 | 1 | 5.75 |  | 0.9 | 5.175
Total | [7 empty] | 5.175
12 | Pointing Paint
| wall | paint | m2 | 1 | 101 |  | 0.5 | 50.5
Total | [7 empty] | 50.5
12 | PVC Doors
| D1 |  | m2 | 1 | 3.8 |  | 2.5 | 9.5
| D2 |  |  | 2 | 2 |  | 2.5 | 10
Total | [7 empty] | 19.5
12 | Skirt Wall
| wall |  | Lm | 1 | 160 |  |  | 160
Total | [7 empty] | 160

## Summary
Summary of (Safar Mohammad Shioon High School)
The cost for all items in this BOQ, in general, includes deploying any machinery, and manpower, and carrying out any relocations/ removal/ salvage/ disposal /reinstating tasks. The costs of checking and testing for all items and materials that need to be used should be included in the relevant unit cost of related items. However, particular issues with the costs of items are mentioned under each section in this BOQ. Details of work method & and equipment/machinery for different types of work shall be brought to the attention of the Engineer to get approval of the Engineer before commencing the jobs. Read all project documents before pricing the job. Changes in market prices during the project period for any item are the responsibility of the Contractor without any extra payment. For all the finishing, electrical accessories, structural items & and materials, mechanical accessories/equipment, plumbing-related materials/items, and other equipment that are mentioned in this BoQ and going to be used, samples, product data from manufacturers/companies, certificates should be submitted to Client in charge Engineer and get their approvals from in charge engineer before start the activity or use the materials and accessories in the project. The contractor has to produce the manufacturer approval certificate of the production country for all the major construction materials and the ISO certificate. The contractor must provide samples, mockups, and catalogs for testing/inspection and approval by the site engineer, The Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. The contractor must provide PPE for all laborers, personnel, engineers, and possible visitors to the site.
S.N | Items (Bill) | Cost (AFN)
1 | Total of A. (Renovation) | 0
2 | Total of C. Construction of New 5 seats latrine | 0
| Grand total amount in AFN | 0
`

## Priority 1 ( Renovation)
Renovation of (Safar Mohammad shioon male high school )
The following text outlines important guidelines that must be followed during the project. It is important to clarify that the total cost of all items listed in this BOQ includes the deployment of machinery and manpower, as well as any relocation, removal, salvage, or reinstatement tasks. It is also important to note that the cost of checks and testing for items and materials to be used must be included in the relevant unit cost of related items. However, specific issues with the costs of items are mentioned under each section in this BOQ. Before commencing any job, details of work methods and equipment/machinery for different types of work must be brought to the attention of the Engineer for approval. Furthermore, it is important to read all project documents before pricing the job. Any changes in market prices during the project period for any item are the contractor's responsibility without any extra payment. To ensure quality and safety, all finishing, electrical accessories, structural items and materials, mechanical accessories/equipment, plumbing-related materials/items, and other equipment mentioned in this BOQ and going to be used must be approved by the Client in charge Engineer before starting the activity or using the materials and accessories in the project. The approval process involves submitting samples, product data from manufacturers/companies, and certificates. The contractor must also provide the manufacturer approval certificate of the production country for all major construction materials and the ISO certificate. Samples, mockups, and catalogs for testing/inspection and approval by the site engineer must be provided by the contractor. The Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. Finally, the contractor must provide Personal Protective Equipment (PPE) for all laborers, personnel, engineers, and visitors to the site to ensure their safety during the project
Badakhshan Jurm Da Safar Mohammad shioon male high school
Priority 1 School Building Revolution
1 - School Building Revolution |  | Unit | Quantity | Unit price (AFN) | Total cast (AFN) | Remark
S.N | Description
A. Civil Works:
A1 | Repairing leakage of a total of 400 Square meters of GI Roof with 24 gage Gi sheets piece, Silicon, and washer screw Prepare all materials, equipment, and manpower for Repairing leakage of a total of 400 Square meters of GI Roof with 24 gage Gi sheets piece, Silicon, and washer screw with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | LS | 1
A2 | Installation of a suspended ceiling (60x60cm for rooms and hall with all T and L shapes with 1mm wire Prepare all materials, equipment, and manpower for the Installation of suspended ceiling (60x60cm for rooms and hall with all T and L shapes with 1mm wire with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | M3 | 325.44
A3 | Removing existing damaged Classroom floor, Corridor floor, and stairs PCC Prepare all materials, equipment, and manpower for Removing the existing damaged Classroom floor, Corridor floor, and stairs PCC with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | m3 | 65.09
A4 | Graval Work ( 10cm): under Class rooms floor ,Corridor floor and PCC Prepare all materials, equipment, and manpower for stone pitching with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M3 | 28.01
A5 | PCC work Mark 200 1:1.5:3 forClass rooms floor ,Corridor floor and stair's PCC Prepare all materials, equipment, and manpower for Removing existing damaged stair's PCC and PCC work including best quality of sand, fresh cement, clean water and crash gravel with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M3 | 44.87
A6 | Repairing of wooden door size 14(100x265)cm with best quality wood including replacement of broken door hardware and glass and oil painting 3 coats Prepare all materials, equipment, and manpower for Repairing of wooden door size 14(100x265)cm with best quality wood including replacement of broken door hardware and glass and oil painting 3 coats with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Job | 1
A7 | Adjusting and repairing Metal Door size 1(300 x265)cm and replacement of door hand tools and lock with oil paint 3 coats Prepare all materials, equipment, and manpower for Adjusting and repairing Metal Door size 1(300 x265)cm and replacement of door hand tools and lock with oil paint 3 coatswith all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Job | 1
A8 | Adjusting and repairing wooden Window size 48(100 x120)cm and replacement of broken window hardware and glass and oil painting 3 coats Prepare all materials, equipment, and manpower for Adjusting and repairing wooden Window size 48(100 x120)cm and replacement of broken window hardware and glass and oil painting 3 coats with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Job | 1
A9 | Wall interior and exterior 100% Plastic Paint three coats Prepare all materials, equipment, and manpower for the wall 100% Plastic Paint three coats (Jotun or equivalent) including preparation, primer, and filling with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | m2 | 200
A10 | Installation of fly screen for 48 windows 29m2 Prepare all materials, equipment, and manpower for the Installation of the fly screen for 48 windows 29m2 with all related activities to complete the job as per the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | m2 | 29
A11 | Cleaning of the project site from extra soil, grass, and materials Prepare all materials, equipment, and manpower for Cleaning the project site from extra soil, grass, and materials with all related activities to complete the job as per the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | LS | 1
A12 | Donor Metal Sign Board 120x80cm as per design and drawings | PIC | 1
Total for School Building Revolution |  |  |  |  | 0

## Priority 3(5 seats latrine)1
Construction of 5 sets latrines for (Safar Mohammad Shioon High School)
The following text outlines important guidelines that must be followed during the project. It is important to clarify that the total cost of all items listed in this BOQ includes the deployment of machinery and manpower, as well as any relocation, removal, salvage, or reinstatement tasks. It is also important to note that the cost of checks and testing for items and materials to be used must be included in the relevant unit cost of related items. However, specific issues with the costs of items are mentioned under each section in this BOQ. Before commencing any job, details of work methods and equipment/machinery for different types of work must be brought to the attention of the Engineer for approval. Furthermore, it is important to read all project documents before pricing the job. Any changes in market prices during the project period for any item are the contractor's responsibility without any extra payment. To ensure quality and safety, all finishing, electrical accessories, structural items and materials, mechanical accessories/equipment, plumbing-related materials/items, and other equipment mentioned in this BOQ and going to be used must be approved by the Client in charge Engineer before starting the activity or using the materials and accessories in the project. The approval process involves submitting samples, product data from manufacturers/companies, and certificates. The contractor must also provide the manufacturer approval certificate of the production country for all major construction materials and the ISO certificate. Samples, mockups, and catalogs for testing/inspection and approval by the site engineer must be provided by the contractor. The Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. Finally, the contractor must provide Personal Protective Equipment (PPE) for all laborers, personnel, engineers, and visitors to the site to ensure their safety during the project
Badakhshan Jurm Da Safar Mohammad Shioon High School
Priority 3 Construction of latrine with 5 cells
C - Construction of latrine |  | Unit | Quantity | Unit price (AFN) | Total cast (AFN) | Remark
S.N | Description
C. Civil Works:
B1 | Excavation of foundation & walkways in Grad 3 land Prepare all materials, equipment, and manpower for excavation of foundation in type 3 land with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 30
B2 | Stone Masonry of foundation with 1:5 mortar Prepare all materials, equipment, and manpower for stone masonry work in foundation with cement ratio 1:5 with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 27
B3 | Supper Stone Masonry with cement mortar 1:4 Prepare all materials, equipment, and manpower for stone masonry work top of the foundation with cement ratio 1:4 with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 43
B4 | RCC(1:1.5:3) rings on the top of stone masonry 20cm Prepare all materials, equipment, and manpower for casting 20 MPA RCC for rings on top of the stone masonry work including steel bending work, curing, formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 4.5
B5 | Filling of flooring with soil including compaction 35cm Prepare all materials, equipment, and manpower for back filling of flooring with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 13.3
B6 | Filling of floor & walkways with gravel including compaction 15cm. Prepare all materials, equipment, and manpower for back filling of flooring and walkways with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 5
B7 | Bricks masonry burnt bricks with (1:5) mortar 35 cm Prepare all materials, equipment, and manpower for burnt brick wall with mortar 1:5 for 35, 25cm wall with formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 27
B8 | Prepare RCC(1:1.5:3) rings on the top of brick masonry 20cm Prepare all materials, equipment, and manpower for casting 20 MPA RCC for rings top of the brick masonry wall including steel bending work, curing, formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 2.25
B9 | PCC(1:2:4) of flooring, stair & walkways ( Mark 150) with 10 cm thickness Prepare all materials, equipment, and manpower for casting 15 MPA PCC for floors, sidewalk and ramp with formworks and surface preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Cum. | 6.8
B10 | Steel I beam and lintel #14 Prepare all materials, equipment, and manpower for steel I BM #14cm with welds and all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M/L | 48
B11 | Oil painting of steel I beam 2 coat. Prepare all materials, equipment, and manpower for I BMs oil painting with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M/L | 48
B12 | Planking work over wooden beam ( thickness 3 cm). Prepare all materials, equipment, and manpower for wooden plank 3cm on I BM with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 24
B13 | Mat( Borya) work over planking. Prepare all materials, equipment, and manpower for Mat (Borya) on planking with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 24
B14 | Clay and dry soil over Mat( Borya) 15 cm Thick. Prepare all materials, equipment, and manpower for Mat (Borya) on planking with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 24
B15 | Wooden truss with Iron sheeting front Khar wood and 24 gauge intron sheet Prepare all materials, equipment, and manpower for wooden truss and iron sheet 24G with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 33.5
B16 | Mud plaster ( kagel) 2 coats including plastic one layer Prepare all materials, equipment, and manpower for straw mud plaster with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 27
B17 | Making and installation of prefabricate slab according to the drawing Prepare all materials, equipment, and manpower for providing and installing of prefabricate slab with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Ea. | 12
B18 | Gutters work (Vertical from GI sheet 24 gage 10X15 cm) Prepare all materials, equipment, and manpower for gutters GI sheet 24 G 10x15cm with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | M/L | 8
B19 | Inside Plaster work (1:4) Mortar with smooth finishing (Namd Mali) Prepare all materials, equipment, and manpower for plastering 1:4 with 2cm thickness including curing, best surfacing preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 118
B20 | White washing in inside with 65% emulsion Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 60% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 118
B21 | Carpentry work (Making of Window Complete) Prepare all materials, equipment, and manpower for carpentry work with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 4.4
B22 | Carpentry work (Making of single doors Complete) Prepare all materials, equipment, and manpower for carpentry work with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 9.4
B23 | Oil painting of windows and doors( 3 coats) Prepare all materials, equipment, and manpower for window and door oil painting with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 27.5
B24 | Installation of glasses 4mm with chufti Prepare all materials, equipment, and manpower for installation of glasses 4mm with chufti and other related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 4.4
B25 | Out side plaster work (with 1: 4 motor) and smooth finishing (Namad mali) Prepare all materials, equipment, and manpower for plastering 1:4 with 2cm thickness including curing, best surfacing preparation with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | Sqm. | 83.5
B26 | White washing with 100 % plastic emulsion (outside) Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 100% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 78
B27 | Installation of fly screen with chufti complete Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 100% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 2
B28 | Pointing with 1:3 mortar Prepare all materials, equipment, and manpower for the preparation of wall surfaces with Primer and filling and Paint the interior and exterior wall with 100% plastic paint with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | Sqm. | 55
B29 | Making of handrail Prepare all materials, equipment, and manpower for the preparation of 10.5m length 80cm high and Painting of Steel handrails with oil paint on three coats with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | M/L | 10.5
B30 | PVC 4 inch pipe for ventilation Prepare all materials, equipment, and manpower for installation of 4inch PVC pipe for ventilation with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | M/L | 25
B31 | Preparation and Installation GI water tank 30x60x105cm and sank in the corridor. Prepare all materials, equipment, and manpower for installation of water tank and sank in corridor with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | Ea. | 1
B32 | Preparation and Installation grabs Prepare all materials, equipment, and manpower for supplying and installation of grabs with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | Ea. | 2
| Total of C1. c32Civil Works: |  |  |  | 0

## B. Latrine renovation (hidden)
Renovation of ( Toryab Keshindara Boys and Girls High School )
The cost for all items in this BOQ, in general, includes deploying of any machineries, manpower, carrying out of any relocations/ removal/ salvage/ disposal /reinstating tasks. The costs of check and testing's for all items and materials needs to be used should be included in the relevant unit cost of related items. However, particular issues to the costs of items mentioned under each section in this BOQ. Details of work method & equipment/machinery for different types of work shall be brought to the attention of Engineer to get approval of Engineer before commencing the jobs. Read given all project document before pricing the job. Changes of market prices during project period for any item is to the responsibility of the Contractor without any extra payment. For all the finishing, electrical accessories, structural items & materrials,mechnial accessories/equipment, plumbing related materials/items and other equipment's which are mentioned in this BoQ and going to be used ,samples, product data from manufactures/companies, certificates should be submitted to Client in charge Engineer and get their approvals from in charge engineer prior to start the activity or use the materials and accessories in the project. Contractor have to produce the manufacturer approval certificate of the production country for all the major construction materials and ISO certificate. The contractor must provide samples, mockups, catalogues for testing / inspection and approval by the site engineer, Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. The contractor must provide PPE for all laborers, personnel, engineers and possible visitors to the site.
S/N | Description | Unit | Quantity | Unit price (AFN) | Total cost (AFN) | Remark
B. Latrine renovation
B1 | Roofing work including "Wooden truss + GI sheet and gutters" Prepare all materials, equipment, and manpower for providing roof wooden truss and GI sheet 24 gage, gutter, Silicon, and washer screw with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | m2 | 80.685 | 2000 | 161370
B2 | Brick masonry work mortar ratio 1:5 for picks Prepare all materials, equipment, and manpower for brick masonry work with all related activities to complete the job as per drawing and instruction of the in-charge engineer all waste materials and debris are to be transported to the approved damp site. All tasks for this item are to be under the full approval of the charge engineer | m3 | 2.2 | 4000 | 8800
B3 | Interior and exterior wall cement plaster 1:4 Prepare all materials, equipment, and manpower for interior and exterior wall cement Plaster 1:4 including during an with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | M2 | 13.86 | #REF! | #REF!
B4 | Supply and installation of metal door complete Prepare all materials, equipment, and manpower for metal door including door hardware and lock with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | M2 | 6 | 1200 | 7200
B5 | Supply and installation of metal window complete. Prepare all materials, equipment, and manpower for metal window size 6(0.5x0.5)m including window hardware and handle, glasses with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | M2 | 1.5 | 1200 | 1800
B6 | Wall interior and exterior 100% Plastic Paint three coats Prepare all materials, equipment, and manpower for the wall 100% Plastic Paint three coats (Jotun or equivalent) including preparation, primer, and filling with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item are to be under full approval in charge engineer | M2 | 237.624 | 0 | 0
B7 | Painting of metal doors and metal windows with oil paint 3 coats Prepare all materials, equipment, and manpower for preparation of windows and door surfaces with Primer and filling and Paint the wooden doors and windows with oil paint 3 coats with all related activities to complete the job as per drawing and instruction of the in-charge engineer All tasks for this item to be under full approval in charge engineer | M2 | 13.5 | 200 | 2700
| Total B. Water System & Sewer System |  |  |  | #REF!

## D. new latrine IDS (hidden)
Renovation of ( Toryab Keshindara Boys and Girls High School )
The cost for all items in this BOQ, in general, includes deploying of any machineries, manpower, carrying out of any relocations/ removal/ salvage/ disposal /reinstating tasks. The costs of check and testing's for all items and materials needs to be used should be included in the relevant unit cost of related items. However, particular issues to the costs of items mentioned under each section in this BOQ. Details of work method & equipment/machinery for different types of work shall be brought to the attention of Engineer to get approval of Engineer before commencing the jobs. Read given all project document before pricing the job. Changes of market prices during project period for any item is to the responsibility of the Contractor without any extra payment. For all the finishing, electrical accessories, structural items & materrials,mechnial accessories/equipment, plumbing related materials/items and other equipment's which are mentioned in this BoQ and going to be used ,samples, product data from manufactures/companies, certificates should be submitted to Client in charge Engineer and get their approvals from in charge engineer prior to start the activity or use the materials and accessories in the project. Contractor have to produce the manufacturer approval certificate of the production country for all the major construction materials and ISO certificate. The contractor must provide samples, mockups, catalogues for testing / inspection and approval by the site engineer, Contractor will bear the cost for samples, including any laboratory tests, both inside and outside the country, as required. The contractor must provide PPE for all laborers, personnel, engineers and possible visitors to the site.
S/N | Description | Unit | Quantity | Unit price (AFN) | Total cost (AFN) | Remark
D. Construction of new 5 cells latrine for girls
D1 |  |  |  |  | 0
D2 |  |  |  |  | 0
D3 |  |  |  |  | 0
D4 |  |  |  |  | 0
D5 |  |  |  |  | 0
| Total D. HVAC works |  |  |  | 0